# Perplexity

Today 12:09 AM

Create a full end to end, step by step plan/to-do list with detailed instructions, llm prompts, etc to get from 0 today to final presentation ready zoom instruction site on my server, including setup and presentation operating instructions to present the pages but keep my script hidden etc. i want everything to be as automated/llm created as possible with the goal scheduling a full cohort as soon as possible... whatever that timeframe is. advise on best steps, best llms to use per step, best doccumentation/backup methods for sureserver/g-drive. again and end to end scope and execution step by step plan.

# CAMERA Live Teaching Site: End-to-End Execution Plan

Yes—build this as a custom, browser-based live teaching system on your SureServer account, not as a conventional deck. The fastest realistic launch is a founding cohort scheduled 3–4 weeks from today, with a five-session / 10-hour course and a polished, complete first delivery system. If you work very intensively and keep the first version strictly scoped, you could open enrollment in 7–10 days and deliver the cohort in 21 days.

Your objective is not to finish the entire 75-chapter CAMERA knowledge system before selling. Your objective is to build:

- A sellable founding-cohort offer.

- A five-session live curriculum.

- A private presenter-only teaching site.

- A student workbook and home-study packet.

- A reliable Zoom presentation procedure.

- A backup system that protects your work.

- A simple payment, registration, onboarding, and delivery path.

The full textbook, advanced modules, protected self-guided course, certification, and complete LMS can follow after the first paid cohort validates the curriculum.

## Launch target

## Recommended founding offer

CAMERA™ Authority Media Training: Internal Content Capability Intensive

A live, interactive five-session virtual program for businesses that want to develop the internal capability to plan, create, present, produce, edit, publish, and sustain their own authority content.

Initial format

| Item | Recommendation |
| --- | --- |
| Delivery | Live Zoom Meetings |
| Cohort length | Five weeks |
| Class schedule | One 2-hour session per week |
| Live instruction | 10 hours total |
| Class size | 5–12 paid seats, or 3–6 business accounts |
| Student materials | Workbook, selected home-study chapters, templates, checklists, 30-/90-day plan |
| Replays | Available for 30 days only, if included |
| Founding price | $697 per person, or $1,750 per company for up to three attendees |
| Founding-seat limit | 10 individual seats or 5 company accounts |
| Enrollment period | 14–21 days |
| Course start | Three to four weeks after first public announcement |

## What must be complete before you sell

You do not need the entire presentation system finished before enrollment opens.

Before announcing the cohort, you need:

- A clear offer and curriculum.

- A date and time.

- A price.

- A checkout or invoice process.

- A one-page registration landing page.

- A polished outline of the five sessions.

- A student outcome list.

- At least Session 1 fully built.

- A credible statement that the workbook, templates, gear guides, and home-study readings are included.

Before the first session begins, you need:

- All five sessions built and tested.

- The student workbook complete enough to support all five modules.

- The Zoom meeting links, registration, reminders, and calendar invitations ready.

- Your teaching site deployed privately to the server.

- An offline backup copy tested.

- A simple student-resource distribution system.

## Recommended tool stack

Use the smallest practical stack. Avoid turning course creation into another multi-tool production workflow.

| Need | Recommended Tool | Why |
| --- | --- | --- |
| Master curriculum and scripts | Google Docs | Easy drafting, commenting, version history, collaboration, PDF export |
| Chapter map, asset register, build tracker | Google Sheets | Track status, file names, module order, assets, workbook pages, and revisions |
| Teaching-site code generation | Claude Pro for one month, if affordable | Best primary “work-order” tool for long source files, structured writing, HTML/CSS/JS/PHP generation, refactoring, and project continuity |
| Secondary LLM reviewer | ChatGPT Projects or Google AI Studio | Use only for review, alternate implementation ideas, prompt refinement, and checking omissions |
| Local coding environment | VS Code | Free, stable, suitable for PHP/HTML/CSS/JS |
| Local web testing | XAMPP or Laragon on Windows | Lets you test PHP teaching pages before uploading to SureServer |
| Live teaching presentation layer | Custom PHP + Reveal.js | Gives you keyboard navigation, presenter notes, progressive reveals, full-screen presentation, PDF backup, and speaker view |
| Web host | Existing SureServer shared hosting | Keeps costs low and gives you ownership |
| File transfer | cPanel File Manager or FileZilla/SFTP | Upload only tested releases |
| Live delivery | Zoom paid Meetings plan | Interactive cohort, screen sharing, breakout options, recording, registration |
| Payments | Stripe Payment Link, PayPal invoice, or an invoice you already use | Fastest path to payment without first building an LMS |
| Workbook distribution | Google Drive shared folder or protected site download page | Fast, low-cost, revisable |
| Course operations | Google Calendar + Gmail + Google Sheets | Simple enrollment, reminders, session tracking, and follow-up |
| Backup archive | Google Drive + local external drive if available | Use redundant copies; do not rely only on the host |

A paid ChatGPT plan includes Projects and Canvas capabilities for managing documents, code, and layouts, with Projects available across qualifying plans. Claude’s paid individual tier is commonly around $20/month and is useful for code-heavy work, long project context, and iterative project files; keep it for only the build month if cost matters.

If you cannot pay for any LLM subscription, use Google AI Studio’s free Gemini tier for structured code batches, but work in smaller files and maintain stricter manual review. Google AI Studio offers a usable free API tier with rate limits rather than requiring a paid subscription from the start.

## Use one primary LLM

Do not make five AIs responsible for the same project.

Recommended primary choice: Claude Pro for one month.

Use it for:

- Condensing textbook material into approved presenter scripts.

- Creating teaching-site scene plans.

- Generating PHP, HTML, CSS, JavaScript, and Reveal.js files.

- Building your reusable component system.

- Troubleshooting code errors.

- Writing speaker notes.

- Producing workbook pages.

- Generating exercise instructions.

- Creating QA checklists.

- Writing student onboarding emails and landing-page copy.

Use ChatGPT or Gemini only as a second opinion when:

- You want a code review.

- You need a second visual-structure option.

- Claude generates an error twice.

- You need help diagnosing a deployment issue.

- You need to compare two versions of a lesson or prompt.

Do not repeatedly regenerate the same page in several tools. That wastes time and creates incompatible visual styles.

# Phase 0: Establish the Control System

Time required: 3–5 hours
Deliverable: One organized project workspace before you begin generating materials.

## Step 0.1 — Create the Google Drive folder structure

Create one top-level folder:

text

CAMERA_V1_MASTER/

Inside it, create the following folders exactly:

text

CAMERA_V1_MASTER/

│

├── 00_ADMIN_AND_VERSION_CONTROL/

├── 01_MASTER_CURRICULUM/

├── 02_LIVE_COHORT_V1/

├── 03_PRESENTER_SCRIPTS/

├── 04_WORKBOOK/

├── 05_TEACHING_SITE_SOURCE/

├── 06_TEACHING_SITE_RELEASES/

├── 07_VISUAL_ASSETS/

├── 08_STUDENT_MATERIALS/

├── 09_MARKETING_AND_SALES/

├── 10_COHORT_OPERATIONS/

├── 11_RECORDINGS_AND_REPLAYS/

├── 12_TESTING_AND_QA/

├── 13_ARCHIVE/

└── 99_EMERGENCY_BACKUPS/

Create these subfolders inside 05_TEACHING_SITE_SOURCE/:

text

05_TEACHING_SITE_SOURCE/

│

├── 00_DESIGN_SYSTEM/

├── 01_CORE_SITE_SHELL/

├── 02_MODULE_01_DIAGNOSIS/

├── 03_MODULE_02_CHARACTER_AUDIENCE/

├── 04_MODULE_03_MONETIZATION_ENGAGEMENT/

├── 05_MODULE_04_PRODUCTION/

├── 06_MODULE_05_OPERATING_SYSTEM/

├── 07_PRESENTER_NOTES/

├── 08_COMPONENT_LIBRARY/

├── 09_BACKUP_PDF/

└── 10_DEPLOYMENT_FILES/

## Why this matters

Your assets will multiply rapidly: textbook chapters, script revisions, slides/scenes, visual assets, workbook pages, code, screenshots, recordings, emails, student submissions, and revised releases. If they are not controlled from day one, you will lose time looking for files and risk presenting the wrong version.

Google Drive maintains revision history for Google Docs, Sheets, and Slides, so you can review or restore prior edits. However, keep independent dated snapshots of major milestones because version-history retention and behavior can vary by file type and settings.

## Step 0.2 — Set a strict naming convention

Use this pattern for every asset:

text

CAMERA_V1_[ASSETTYPE]_[MODULE]_[LESSON]_[DESCRIPTION]_v01_YYYY-MM-DD

Examples:

text

CAMERA_V1_SCRIPT_M01_L01_What_CAMERA_Is_v01_2026-09-23

CAMERA_V1_WORKBOOK_M01_Content_Assessment_v01_2026-09-23

CAMERA_V1_SITE_M01_L02_Stop_Starting_With_the_Camera_v01_2026-09-23

CAMERA_V1_DECK_M04_Production_Foundations_v01_2026-10-04

CAMERA_V1_RELEASE_LIVE_SITE_v01_2026-10-10.zip

CAMERA_V1_COHORT_01_Student_Onboarding_Email_v01_2026-10-11

Never use names such as:

text

new version

final final

final v2 actually final

camera stuff

module maybe done

## Version convention

- v01 = first usable version.

- v02 = meaningful revision.

- v03 = revised after internal test.

- v1.0 = frozen founding-cohort release.

- v1.1 = minor post-cohort correction.

- v2.0 = major curriculum or design-system change.

## Step 0.3 — Create the Master Asset Register

In Google Sheets, create:

text

CAMERA_V1_MASTER_ASSET_REGISTER

Use these columns:

| Column | What it tracks |
| --- | --- |
| Asset ID | Example: M01-L02-SC03 |
| Asset Type | Script, workbook, code, image, diagram, checklist, video, email |
| Module | 1–5 |
| Lesson | Lesson title |
| Scene / Page | Exact scene number or route |
| Source Chapter(s) | Master textbook chapters used |
| Student Outcome | What the learner should understand or do |
| File Name | Exact current file name |
| Google Drive URL | Link to source asset |
| Server Route | Example: /camera-live/m1/diagnosis/ |
| Build Status | Not started / Draft / Review / Tested / Approved / Deployed |
| LLM Used | Claude / ChatGPT / Gemini / Manual |
| Last Updated | Date |
| QA Status | Not tested / Desktop tested / Zoom tested / Approved |
| Notes | Problems, future revisions, missing visual asset |

Create the following status colors:

- Gray: Not started.

- Yellow: In progress.

- Orange: Needs review.

- Blue: Tested.

- Green: Approved and deployed.

- Red: Broken or requires correction.

This spreadsheet is the operating dashboard for the entire course build.

## Step 0.4 — Freeze the current master TOC

Create a Google Doc named:

text

CAMERA_V1_MASTER_TOC_FROZEN_v1.0_2026-09-23

Paste in the full Table of Contents you supplied.

At the top, insert:

text

STATUS: FROZEN MASTER STRUCTURE — VERSION 1.0

DATE FROZEN: September 23, 2026

PURPOSE: This is the governing structure for CAMERA V1.

CHANGE RULE: Do not edit this document casually. Proposed additions,

deletions, or reordering must be recorded in the CAMERA V1 Change Log.

Create a separate Google Doc:

text

CAMERA_V1_CHANGE_LOG

Use these headings:

text

Change ID:

Date:

Requested by:

Affected Chapter / Module:

Current Version:

Proposed Change:

Reason:

Impact on Book:

Impact on Workbook:

Impact on Presenter Script:

Impact on Teaching Site:

Decision:

Approved By:

Implementation Date:

This prevents the master course from continuously expanding while you are trying to sell the first cohort.

# Phase 1: Define the Founding Cohort

Time required: 1–2 days
Deliverable: A specific, sellable, five-session program.

## Step 1.1 — Lock the Version 1 live format

Use this format for the first cohort:

| Session | Name | Duration | Primary Outcome |
| --- | --- | --- | --- |
| 1 | Diagnose the Business Content Need | 2 hours | Determine what content capability the business needs and identify its current gap |
| 2 | Define Authority and Audience | 2 hours | Select who speaks, what authority they possess, and whom they must help |
| 3 | Connect Content to Business Results | 2 hours | Build content pillars, content-to-offer paths, CTAs, and useful hooks |
| 4 | Build and Deliver Professional-Enough Content | 2 hours | Create a practical on-camera, camera, lighting, audio, background, and video structure plan |
| 5 | Build the Internal Content Operating System | 2 hours | Build workflow, repurposing, minimal tools, AI process, measurement, 30-day plan, and 90-day plan |

Total live teaching time: 10 hours.

## First-cohort scope rule

The founding cohort is not responsible for producing polished videos for every attendee during class. The course teaches, demonstrates, corrects, and equips students to produce content after each session.

The central completion artifact is:

The CAMERA Business Content System
A student-built operating binder containing their authority definition, audience map, offer map, content pillars, script ideas, starter setup, gear/software plan, workflow, repurposing system, AI workflow, 30-day schedule, and 90-day improvement plan.

## Step 1.2 — Create the curriculum map

Create a Google Sheet:

text

CAMERA_V1_LIVE_COHORT_CURRICULUM_MAP

Use these columns:

| Session | Master Chapters | Teach Live | Demonstrate | Live Exercise | Homework | Workbook Pages | Teaching-Site Scenes | Completion Evidence |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

Enter this core map:

| Session | Core Master Chapters |
| --- | --- |
| 1 | Chapters 1, 2, 32 |
| 2 | Chapters 4, 5, 6, 7 |
| 3 | Chapters 8, 9, 10, 11 |
| 4 | Chapters 12, 13, 14, 15, 16, 17, 18 |
| 5 | Chapters 19, 20, 21, 22, 29, 30, 31, 32, 33, 43, 44, 47, 48, 50, 51, 56 |

This is your live-course boundary. Everything else remains in the Master Textbook, Resource Handbook, advanced modules, self-guided course, or future premium implementation tiers.

## Step 1.3 — Create the founding-cohort offer document

Create a Google Doc:

text

CAMERA_V1_FOUNDING_COHORT_OFFER_v01

Paste and revise this core offer statement:

CAMERA™ Authority Media Training: Internal Content Capability Intensive
A live five-week training program for business owners, founders, professionals, spokespersons, and content teams who want to build the ability to create effective authority content internally—without depending on agencies or production houses for every video, social post, or marketing asset.

Participants will leave with a practical business content system: a defined authority position, audience map, content strategy, scripts and hooks, a realistic production setup, a gear and software plan, an internal workflow, an AI-assisted process, a 30-day publishing plan, and a 90-day implementation roadmap.

## Founding cohort inclusions

- Ten hours of live Zoom instruction.

- Five live interactive workshops.

- CAMERA Live Cohort Workbook.

- Selected Master Textbook home-study assignments.

- Starter gear and software decision guides.

- Script, hook, CTA, and content-calendar templates.

- AI prompt and verification workflow.

- Thirty-day replay access, if included.

- Final Business Content System completion checklist.

- Optional limited instructor feedback window.

## Suggested founding pricing

Use either of these structures:

| Option | Recommended Price | Best For |
| --- | --- | --- |
| Individual Seat | $697 | Founder, professional, one-person operation |
| Company Access | $1,750 | One company with up to three attendees |
| Founding Upgrade | Add $500–$750 | Includes one 45–60 minute private implementation review |
| Premium Upgrade | Add $1,500+ | Includes setup review, script review, and 30-day follow-up feedback |

Do not lead with a cheap price. You are not selling generic “social media tips.” You are selling a business capability system and the benefit of 30 years of production, broadcast, and marketing judgment.

# Phase 2: Build the Documents Before Code

Time required: 4–7 days
Deliverable: Approved scripts, workbook sections, and scene specifications.

Do not begin asking an LLM for a large PHP site before creating the teaching blueprint. The course documents control the site—not the other way around.

## Step 2.1 — Create one Live Session Blueprint document per session

Create five Google Docs:

text

CAMERA_V1_LIVE_SESSION_01_BLUEPRINT

CAMERA_V1_LIVE_SESSION_02_BLUEPRINT

CAMERA_V1_LIVE_SESSION_03_BLUEPRINT

CAMERA_V1_LIVE_SESSION_04_BLUEPRINT

CAMERA_V1_LIVE_SESSION_05_BLUEPRINT

Use this exact structure in each.

text

SESSION TITLE:

SESSION LENGTH:

120 minutes

PRIMARY CAMERA DIMENSIONS:

MASTER CHAPTER SOURCES:

STUDENT OUTCOME:

By the end of this session, students will be able to...

LIVE DELIVERABLE:

Students will complete...

HOMEWORK:

Students will complete...

REQUIRED WORKBOOK PAGES:

REQUIRED TEACHING-SITE SCENES:

REQUIRED VISUAL DEMONSTRATIONS:

REQUIRED EXAMPLES OR CASE STUDIES:

MATERIALS / ASSETS NEEDED:

SESSION AGENDA:

00:00–00:10 Opening, welcome, objective, prior-session recall

00:10–00:35 Teaching block 1

00:35–00:50 Demonstration

00:50–01:10 Workbook exercise

01:10–01:20 Break

01:20–01:45 Teaching block 2

01:45–02:00 Practice, Q&A, homework, close

COMMON STUDENT MISTAKES:

INSTRUCTOR CAUTIONS:

ASSESSMENT / COMPLETION EVIDENCE:

HOME-STUDY READING:

## Step 2.2 — Create the Presenter Script template

Create a Google Doc:

text

CAMERA_V1_PRESENTER_SCRIPT_TEMPLATE

Paste this format:

text

MODULE:

LESSON:

SCENE NUMBER:

SCENE TITLE:

TARGET TIME:

STUDENT OUTCOME:

OPENING:

What do I say to establish relevance?

CORE PRINCIPLE:

What must students understand?

EXPLANATION:

What do I teach in full spoken language?

EXPERIENCE / STORY:

What do I know from production, broadcast, or marketing work that proves this point?

BUSINESS EXAMPLE:

What does this look like in a real business?

COMMON MISTAKE:

What usually goes wrong?

DEMONSTRATION:

What should I show visually?

WORKBOOK INSTRUCTION:

Exact page and exact action the student takes.

DISCUSSION QUESTION:

Question to ask the room.

EXPECTED RESPONSES:

Likely participant answers.

TRANSITION:

Exact bridge to the next scene.

VISUAL BRIEF:

What should be on the teaching site scene?

## Presenter-script creation workflow

For each live session:

- Copy only the relevant master-chapter material into a working document.

- Highlight:

  - Principles that must be taught live.

  - Examples that must be shown.

  - Decisions the participant must make.

  - Exercises that must happen in class.

  - Detail that becomes assigned reading.

- Ask the LLM to create a first script draft.

- Edit the result manually in your voice.

- Add your real stories, warnings, examples, and opinions.

- Approve the script before any site code is generated.

- Create the slide/scene plan from the approved script.

## Core script-generation prompt

text

You are assisting with the CAMERA™ Authority Media Training System.

Your job is to convert approved Master Textbook material into a live,

instructor-led teaching script. This is not a summary, not a blog post,

not a webinar pitch, and not a slide deck.

Audience:

Business owners, founders, professionals, spokespersons, and small content teams

who want to build internal capability to create useful authority content rather

than repeatedly outsource every content need.

Course standard:

Premium executive education combined with practical media training.

Direct, concrete, visually literate, and evidence-based.

No generic AI language. No motivational filler. No influencer jargon.

Session:

[INSERT SESSION NAME]

Chapter:

[INSERT SCENE TITLE]

Student outcome:

[INSERT ONE SPECIFIC OUTCOME]

Source material:

[PASTE ONLY THE RELEVANT MASTER TEXTBOOK SECTION]

Required output:

1. A 5–8 minute spoken presenter script.

2. One strong opening hook.

3. A clear teaching principle.

4. A real-business example.

5. One common mistake and correction.

6. Workbook instructions.

7. One audience question.

8. A transition sentence.

9. A short visual brief for a web teaching scene.

Important:

- Preserve the substance of the source material.

- Do not invent research, statistics, testimonials, client outcomes, or personal history.

- Mark any statement needing factual verification as [VERIFY].

- Keep the language natural enough to say aloud.

- Do not use phrases such as “unlock,” “game-changing,” “revolutionary,”

“in today’s fast-paced world,” or “leverage cutting-edge.”

## Step 2.3 — Build the live workbook first-pass

Create:

text

CAMERA_V1_LIVE_COHORT_WORKBOOK_v01

It should contain only the pages students need for the five-session program.

## Suggested live-workbook sections

| Workbook Section | Used In |
| --- | --- |
| Student Orientation and Goals | Before Session 1 |
| Current Content Capability Assessment | Session 1 |
| Business Content Requirement Assessment | Session 1 |
| Authority Inventory and Spokesperson Decision | Session 2 |
| On-Camera Identity and Self-Assessment | Session 2 |
| Audience Intent, Questions, and Objection Map | Session 2 |
| Content-to-Offer Map | Session 3 |
| Content Pillars and CTA Library | Session 3 |
| Hook Bank and Five-Video Planning Sheets | Session 3 |
| Video Structure and Script Outline | Session 4 |
| Setup Audit: Camera, Audio, Lighting, Background | Session 4 |
| Gear and Software Decision Pages | Session 4/5 |
| Repurposing Map | Session 5 |
| Internal Workflow Map | Session 5 |
| AI Workflow and Verification Checklist | Session 5 |
| Metrics Scorecard | Session 5 |
| 30-Day Content Plan | Session 5 |
| 90-Day Capability Plan | Session 5 |
| Final Business Content System Summary | End of Session 5 |

## Workbook-generation prompt

text

Create print-friendly and Google-Docs-friendly workbook pages for the

CAMERA™ Authority Media Training live cohort.

Module:

[INSERT MODULE]

Purpose:

[INSERT WHAT THE WORKBOOK SECTION MUST HELP THE STUDENT DECIDE OR BUILD]

Requirements:

- Use plain professional language.

- Include clear instructions before every exercise.

- Provide enough blank space for typed answers and handwritten answers.

- Use section labels, tables, checkboxes, short prompts, and writing lines.

- Avoid tiny type, dense pages, decorative design, and unnecessary theory.

- Each worksheet must produce a usable business artifact, not merely reflection.

- Include a “What I will do next” implementation box.

- Include a “Instructor feedback / notes” box when useful.

- Make the result ready to paste into Google Docs.

Output:

1. Section title.

2. Student instruction.

3. Worksheet fields.

4. Completion checklist.

5. Instructor review criteria.

## Step 2.4 — Convert scripts into Scene Maps

Create one scene map for each session in Google Sheets.

Example filename:

text

CAMERA_V1_M01_SCENE_MAP

Use these columns:

| Scene ID | Scene Title | Time | Script Source | Visual Component | On-Screen Copy | Visual Asset Needed | Workbook Page | Speaker Notes | Build Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

## Example: Module 1 scene list

| Scene ID | Scene Title | Component |
| --- | --- | --- |
| M01-S01 | Module Opening: Diagnose the Business Content Need | Hero Thesis |
| M01-S02 | CAMERA Is a Business Capability | Thesis / Comparison |
| M01-S03 | The Agency Dependence Problem | Comparison |
| M01-S04 | Stop Starting With the Camera | Side-by-Side Comparison |
| M01-S05 | Start With the Business | Process Flow |
| M01-S06 | The Content Requirement Assessment | Diagnostic Framework |
| M01-S07 | Business Content Models | Decision Tree |
| M01-S08 | Minimum Viable Content Operation | Diagram |
| M01-S09 | Content Capability Ladder | Ladder Diagram |
| M01-S10 | Workbook Exercise: Assess Your Current Capability | Exercise |
| M01-S11 | Discussion and Pattern Recognition | Discussion Prompt |
| M01-S12 | Session One Assignment | Assignment |
| M01-S13 | Session One Recap | Recap |
| M01-S14 | Next Session Preview | Transition |

Use approximately 12–18 scenes per 2-hour module, not 40–60. You are teaching a class, not running a rapid-fire deck.

# Phase 3: Build the Teaching Site Foundation

Time required: 2–4 days
Deliverable: A reusable, tested private presentation shell.

## Step 3.1 — Use a local development environment first

Do not write code directly in SureServer’s File Manager as your primary workflow.

Install one local PHP environment:

- Laragon for the simplest Windows workflow.

- Or XAMPP if you already know it.

Create a local project folder:

text

C:\CAMERA\camera-live\

Recommended project structure:

text

camera-live/

│

├── index.php

├── .htaccess

├── README.md

├── CHANGELOG.md

├── config/

│   ├── course.php

│   ├── routes.php

│   ├── presentation.php

│   └── credentials.example.php

│

├── assets/

│   ├── css/

│   │   ├── reset.css

│   │   ├── tokens.css

│   │   ├── base.css

│   │   ├── layout.css

│   │   ├── components.css

│   │   ├── presenter.css

│   │   ├── motion.css

│   │   └── print.css

│   ├── js/

│   │   ├── app.js

│   │   ├── navigation.js

│   │   ├── presenter-mode.js

│   │   ├── timer.js

│   │   ├── blackout.js

│   │   └── accessibility.js

│   ├── img/

│   ├── video/

│   ├── icons/

│   └── fonts/

│

├── includes/

│   ├── head.php

│   ├── header.php

│   ├── footer.php

│   ├── navigation.php

│   ├── presenter-toolbar.php

│   ├── scene.php

│   ├── components.php

│   └── presenter-notes.php

│

├── modules/

│   ├── module-01.php

│   ├── module-02.php

│   ├── module-03.php

│   ├── module-04.php

│   └── module-05.php

│

├── notes/

│   ├── module-01-notes.php

│   ├── module-02-notes.php

│   ├── module-03-notes.php

│   ├── module-04-notes.php

│   └── module-05-notes.php

│

├── presenter/

│   ├── index.php

│   ├── login.php

│   └── presenter.css

│

├── student/

│   ├── resources.php

│   └── downloads.php

│

├── vendor/

│   └── revealjs/

│

└── backups/

└── .gitkeep

## Important security rule

Do not store active passwords, API keys, or payment credentials in public web files.

Use a local config file excluded from version control, such as:

text

config/credentials.php

Create a harmless template:

text

config/credentials.example.php

Your credentials.php file should never be uploaded to a public Google Drive folder, pasted into an LLM, or committed to a public code repository.

## Step 3.2 — Use Git locally

Install Git and initialize a local repository:

bash

git init

git add .

git commit -m "Initial CAMERA live teaching site shell"

Then commit at the end of every working block:

bash

git add .

git commit -m "Build M01 scene 04 camera-first comparison"

## Why Git matters

Google Drive is excellent for documents and assets. It is not an ideal source-control system for PHP, CSS, JavaScript, and multiple versions of a web site.

Use:

- Git for code history.

- Google Drive for documents, assets, exported releases, and off-site backup.

- SureServer for deployed, working versions only.

At the end of each day:

bash

git status

git add .

git commit -m "End of day backup YYYY-MM-DD"

Then create a ZIP archive of the entire project and upload it to:

text

Google Drive / CAMERA_V1_MASTER / 06_TEACHING_SITE_RELEASES /

Name it:

text

CAMERA_V1_LIVE_SITE_DEV_BACKUP_YYYY-MM-DD.zip

## Step 3.3 — Use Reveal.js as the invisible presentation engine

Use Reveal.js for:

- Keyboard forward/back navigation.

- Full-screen presentation.

- Progressive content fragments.

- Presenter notes.

- Slide/scene routing.

- PDF print/export option.

- Built-in speaker view.

- Offline-capable local presentation backup.

Reveal.js supports web-native presentations with stepped fragments, auto-animation, and a separate speaker-notes view. Its speaker view can show notes in a separate browser window, which is useful when you need attendees to see only the presentation content.

## Install procedure

- Download the current stable Reveal.js release from its official source.

- Place it inside:

text

camera-live/vendor/revealjs/

- Do not modify library files.

- Put all CAMERA visual changes in your own CSS and component files.

- Keep a copy of the original Reveal.js ZIP in:

text

Google Drive / CAMERA_V1_MASTER / 05_TEACHING_SITE_SOURCE / 01_CORE_SITE_SHELL / third_party_originals/

This lets you reproduce the system later.

## Step 3.4 — Create the visual design system

Before generating pages, create a Google Doc:

text

CAMERA_V1_VISUAL_DESIGN_STANDARD_v01

Then create your CSS token file:

text

assets/css/tokens.css

Use only a restrained visual system.

css

:root {

--camera-black: #111111;

--camera-charcoal: #1d1d1d;

--camera-slate: #353b42;

--camera-paper: #f4f0e8;

--camera-muted: #c6c0b5;

--camera-accent: #b58a42;

--camera-alert: #b64a3b;

--camera-success: #70865a;

--font-display: "YourDisplayFont", Georgia, serif;

--font-body: "YourBodyFont", Arial, sans-serif;

--space-xs: 0.5rem;

--space-sm: 1rem;

--space-md: 1.5rem;

--space-lg: 2.5rem;

--space-xl: 4rem;

--radius-sm: 0.35rem;

--radius-md: 0.75rem;

--shadow-soft: 0 0.8rem 2.2rem rgba(0, 0, 0, 0.25);

}

## Design rules to document

- Dark charcoal or near-black background.

- Warm, readable light text.

- One muted accent color.

- Large editorial typography.

- Strong grid alignment.

- Real examples, diagrams, annotated frames, workflows, and comparisons.

- No cartoon people.

- No generic AI-generated “business” artwork.

- No purple/blue SaaS gradients.

- No dense bullet paragraphs.

- Minimal use of cards.

- No more than one main concept per scene.

- Motion must explain process, sequence, comparison, or cause-and-effect.

## Step 3.5 — Build reusable components

Create these components before building modules:

| Component File | Purpose |
| --- | --- |
| hero-thesis.php | Large concept opening |
| comparison.php | Wrong/right, old/new, agency/internal comparisons |
| process-flow.php | Sequential diagrams |
| framework.php | CAMERA model and other diagrams |
| decision-tree.php | Spokesperson, gear, software, platform decisions |
| annotation.php | Point to visible details in images or screen captures |
| checklist.php | Practical lists |
| workbook-prompt.php | Exercise instructions with workbook page |
| case-study.php | Business-context examples |
| assignment.php | Homework / implementation task |
| recap.php | End-of-session reinforcement |
| transition.php | Section and module breaks |

## Component-generation prompt

text

You are building a reusable PHP component library for the CAMERA™

Authority Media Training live teaching site.

Create the component:

[INSERT COMPONENT NAME]

Purpose:

[INSERT PURPOSE]

Technical environment:

- PHP 8-compatible shared hosting.

- HTML, CSS, vanilla JavaScript only.

- Reveal.js presentation environment.

- No React, Node build system, npm dependency, database, or external API required.

- Must work on ordinary shared hosting.

- Must work with keyboard presentation navigation.

- Must use semantic HTML and accessible labels.

- Must use CSS classes only; do not embed large page-specific CSS blocks.

- Must accept content through a PHP associative array.

- Include a short usage example.

- Include sensible escaping for text output.

- No external stock-image URLs.

- No hidden tracking.

- No unnecessary JavaScript.

Design:

Premium editorial training system. Dark, restrained, high-contrast,

minimal, sophisticated, not a dashboard and not a generic slide deck.

Output:

1. The PHP component file.

2. Expected data-array schema.

3. CSS classes needed.

4. Minimal CSS additions.

5. Example use inside a Reveal.js section.

# Phase 4: Keep Script Hidden While Presenting

Time required: 1–2 days to build and test
Deliverable: A presenter-only control system where Zoom attendees see only the visual teaching pages.

This is the most important operating requirement you mentioned.

## The rule

Never screen-share your entire desktop unless you have no alternative. Share only the audience-facing browser window or browser tab.

Zoom permits sharing a specific application window or browser tab rather than the entire desktop. That lets you keep your presenter notes, Zoom controls, file folders, private prompts, and script documents visible only to yourself.

## Best operating configuration: two displays

The best setup is:

- Your laptop display: presenter control screen.

- Any available second display: television, spare monitor, old computer monitor, or inexpensive used monitor.

- Zoom shares the audience-facing teaching-site window on the second display.

- Your laptop holds:

  - Presenter notes.

  - Zoom participant/chat controls.

  - Google Doc script, if needed.

  - Timer.

  - Workbook and resource links.

  - Your email, if needed.

  - Backup PDF or local offline copy.

## Recommended physical layout

| Screen | What you see | What students see |
| --- | --- | --- |
| Laptop screen | Zoom controls, participant gallery, speaker notes, script, timer | Nothing directly |
| Second monitor | Full-screen audience presentation window | This is the window you share |
| Zoom attendee screen | Only the shared browser window | Teaching site visuals only |

## If you have only one display

You can still do this safely.

- Open the teaching site in one browser window.

- Open speaker notes in a separate browser window.

- Resize the teaching-site window so it is a normal window, not browser full-screen.

- In Zoom, choose Share Screen.

- Select the specific teaching-site browser window—not “Entire Screen.”

- Keep the notes window behind or beside it.

- Use Alt + Tab only after confirming the shared window remains selected.

- Never drag private notes over the shared presentation window.

Zoom’s documentation specifically recommends sharing a particular application window rather than the entire screen when you need to use other applications without interrupting what participants see.

## Recommended hidden-notes design

Use two separate routes:

text

Audience route:

https://yourdomain.com/camera-live/

Presenter route:

https://yourdomain.com/camera-live/presenter/

The audience route contains:

- Slides/scenes.

- Visuals.

- Progressive reveals.

- Exercises.

- Session recaps.

- No script.

- No private notes.

- No student-specific commentary.

- No admin navigation.

The presenter route contains:

- The same current scene.

- Current scene number.

- Full or shortened presenter script.

- Next-scene preview.

- Timer.

- Workbook reference.

- Exercise timing.

- Demonstration instructions.

- Common questions.

- Transition language.

- Keyboard shortcuts.

- Emergency links.

## Presenter route security

For Version 1:

- Use HTTP password protection if available in cPanel.

- Or create a simple PHP login protected by a strong password.

- Do not link to the presenter route publicly.

- Add noindex, nofollow meta tags.

- Block it in robots.txt.

- Use a URL that is not obvious.

- Do not use the same password as email, banking, Google, or hosting accounts.

For a live cohort, attendees should never receive access to the presenter route. They only see it through Zoom screen share.

## Step 4.1 — Build presenter notes as a separate data file

Do not put full scripts inside the visual presentation code.

For each module, create:

text

notes/module-01-notes.php

notes/module-02-notes.php

Example structure:

php

<?php

$presenterNotes = [

'm01-s04' => [

'title' => 'Stop Starting With the Camera',

'time' => '5 minutes',

'objective' => 'Students understand that gear follows strategy.',

'script' => 'The first mistake many businesses make...',

'workbook' => 'Workbook 2, Section 2.1: Business Assessment',

'question' => 'What happens when a business buys gear before defining its content need?',

'expected_responses' => [

'The equipment sits unused.',

'The business creates random content.',

'The team does not know what to say.'

],

'transition' => 'Now that we have stopped starting with the camera...',

'common_mistake' => 'Do not turn this into a technical lecture about cameras.'

],

];

Then your presenter page loads notes based on the current scene ID.

## Presenter-notes prompt

text

Create a presenter-note entry for the CAMERA™ live teaching site.

Scene ID:

[INSERT ID]

Scene title:

[INSERT TITLE]

Approved presenter script:

[PASTE FINAL SCRIPT]

Output in PHP associative-array format with:

- title

- time

- objective

- script

- visual_instruction

- workbook_reference

- audience_question

- expected_responses

- demonstration_instruction

- common_mistake

- transition

- backup_if_short_on_time

Do not change the approved teaching substance.

Do not add claims, statistics, or examples not contained in the source.

## Step 4.2 — Create a presenter view

Your presenter view should be simple:

text

---------------------------------------------------------

CURRENT SCENE: M01-S04 — Stop Starting With the Camera

TIME BUDGET: 5 minutes | SESSION CLOCK: 00:32:18

---------------------------------------------------------

PRESENTER SCRIPT:

[Large readable script text]

WORKBOOK:

Workbook 2, page X — Business Assessment

ASK:

“What happens when a business buys gear before defining...?”

NEXT:

M01-S05 — Start With the Business

SHORTCUTS:

Right Arrow = Next

Left Arrow = Previous

B = Blackout

N = Toggle Notes

T = Timer

F = Full Screen

---------------------------------------------------------

## Essential controls

- Right Arrow = next scene.

- Left Arrow = prior scene.

- Spacebar = advance fragment or scene.

- B = blackout visual screen.

- N = toggle notes.

- T = show/hide timer.

- H = home / module overview.

- ? = keyboard shortcut overlay.

- Esc = exit full-screen presentation safely.

## Blackout use

Use a blackout command when:

- You want students to focus on your face.

- You are handling a sensitive question.

- You are facilitating discussion.

- You are giving a verbal instruction.

- A student is presenting or asking for feedback.

- You must open a separate demonstration resource.

The page should become a clean black or charcoal screen with a small CAMERA mark—not an empty browser interface.

# Phase 5: Generate Module 1 Completely

Time required: 2–4 days
Deliverable: A fully usable 2-hour Session 1 and proof-of-system.

Do not start five modules at once. Build Module 1 completely so you establish:

- The presenter-script format.

- The workbook format.

- The visual design.

- The site templates.

- The hidden-notes system.

- The deployment process.

- The Zoom operating procedure.

- The backup process.

## Step 5.1 — Build Module 1 contents

Module 1: Diagnose the Business Content Need

Master chapter sources:

- Chapter 1 — What CAMERA Is.

- Chapter 2 — The CAMERA Framework.

- Chapter 3 — Determine What Your Business Actually Needs.

Student outcome:

The student can describe what content capability their business requires, identify the gap between their current situation and that capability, and select an appropriate initial content model.

Live student deliverables:

- Business Content Requirement Assessment.

- Current Content Capability Gap.

- Initial internal content model.

- Minimum Viable Content Operation plan.

- Initial 30-day starting objective.

## Module 1 production checklist

- Session Blueprint approved.

- Presenter script approved.

- Workbook pages complete.

- Scene map complete.

- Required visual assets identified.

- Teaching-site scenes generated.

- Presenter notes generated.

- Desktop test complete.

- Zoom test complete.

- Server deployment complete.

- Local offline backup tested.

- PDF backup exported.

- Instructor run sheet created.

## Step 5.2 — Generate scene code in small batches

Build no more than two to four scenes per LLM prompt. Do not ask for the entire module at once.

## Scene-code prompt

text

You are implementing the CAMERA™ live teaching site.

Create these scenes only:

- M01-S04: Stop Starting With the Camera

- M01-S05: Start With the Business

- M01-S06: Content Requirement Assessment

Technical constraints:

- PHP 8 compatible.

- Reveal.js section markup.

- Use existing CAMERA CSS tokens and reusable components.

- No framework, no package manager, no database.

- Do not alter existing global files.

- Output one complete module fragment file only.

- Use semantic HTML.

- Include accessibility labels.

- Provide `data-scene-id` attributes.

- Include presenter-note IDs that correspond exactly to each scene ID.

- Respect `prefers-reduced-motion`.

- Do not embed external media or external image URLs.

- Use placeholders for assets not yet created.

- Keep on-screen copy concise; spoken detail is in presenter notes.

Design requirements:

- Premium editorial training.

- Not a card grid.

- No generic corporate language.

- Strong side-by-side comparison and process visualization.

- One primary concept per scene.

Approved content:

[PASTE APPROVED SCENE MAP AND ON-SCREEN COPY]

## Do not accept code blindly

After each generated batch:

- Paste it into the local project.

- Open the site locally.

- Check navigation.

- Check mobile/responsive behavior only as a secondary concern; desktop Zoom display is primary.

- Check that text is readable at Zoom screen-share size.

- Check that the scene does not overflow vertically.

- Check that long lines do not run off screen.

- Check that speaker notes correspond to the correct scene ID.

- Check that private notes are not loaded in audience mode.

- Commit changes to Git.

## Step 5.3 — Create the first visual asset library

Create this Drive folder:

text

07_VISUAL_ASSETS/

├── 01_CAMERA_AND_FRAMING/

├── 02_LIGHTING/

├── 03_AUDIO/

├── 04_BACKGROUND_AND_SET/

├── 05_EDITING/

├── 06_WORKFLOWS/

├── 07_CONTENT_STRATEGY/

├── 08_REPURPOSING/

├── 09_AI_WORKFLOW/

├── 10_GEAR/

└── 11_CASE_STUDIES/

For Module 1, build only:

- A Camera-First vs Business-Need-First diagram.

- CAMERA six-dimensions diagram.

- Content Capability Ladder.

- Minimum Viable Content Operation diagram.

- Business content-model decision tree.

- Before/after comparison: “random posting” versus “operating system.”

- Workbook exercise graphic.

- Module recap visual.

Use diagrams more than stock photos. Your subject is naturally visual: gear, workflows, framing, lighting, editing, content maps, and production operations.

## Diagram-generation prompt

text

Create a visual specification for a premium instructional diagram.

Topic:

The Minimum Viable Content Operation for a small business.

Audience:

Business owners and small internal teams.

Diagram objective:

Show the smallest sustainable operating system needed to produce useful

internal authority content without hiring an agency for every asset.

Required elements:

- One primary spokesperson or authority source

- One content objective

- One audience/problem focus

- One simple recording setup

- One primary editing method

- One approval step

- One publishing rhythm

- One measurement/review loop

Style:

Editorial field guide / broadcast operations manual.

Dark background, warm white text, muted brass accent, simple lines.

No 3D, no cartoon people, no generic business icons, no gradients.

Output:

1. Diagram layout description.

2. Exact labels.

3. Hierarchy and flow order.

4. Suggested SVG structure or HTML/CSS structure.

5. Alt text.

# Phase 6: Build Modules 2–5 Using the Proven System

Time required: 7–12 days
Deliverable: Complete five-session live teaching site.

Once Module 1 is working, do not redesign the system. Repeat the same production pipeline.

## Module production sequence

| Module | Script | Workbook | Scene Map | Code | Notes | QA | Deployment |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Build first | Build first | Build first | Build first | Build first | Test first | Deploy first |
| 2 | Reuse template | Reuse template | Reuse template | Reuse components | Reuse notes layout | Test | Deploy |
| 3 | Reuse template | Reuse template | Reuse template | Reuse components | Reuse notes layout | Test | Deploy |
| 4 | Reuse template | Reuse template | Reuse template | Reuse components | Reuse notes layout | Test | Deploy |
| 5 | Reuse template | Reuse template | Reuse template | Reuse components | Reuse notes layout | Test | Deploy |

## Module 2 assets

Title: Define Authority and Audience
Core chapters: 4–7
Key visuals:

- Authority versus persona comparison.

- Spokesperson-selection decision tree.

- Authority inventory diagram.

- Camera eye-line comparison.

- Framing examples.

- Audience intent map.

- Buyer questions / objections grid.

- Useful content formats.

- Exercise and assignment scenes.

## Module 3 assets

Title: Connect Content to Business Results
Core chapters: 8–11
Key visuals:

- Content-to-offer map.

- Customer journey / content map.

- Content pillar wheel.

- CTA ladder.

- “Useful hook vs clickbait” comparison.

- Hook formula system.

- 30-day planning flow.

- Five-video planning exercise.

## Module 4 assets

Title: Build and Deliver Professional-Enough Content
Core chapters: 12–18
Key visuals:

- Retention structure diagram.

- Script / outline / teleprompter decision guide.

- Voice and delivery self-assessment.

- Phone versus webcam versus camera matrix.

- Framing diagram.

- Window-light example.

- One-light and two-light setup diagrams.

- Background comparison.

- Microphone-placement illustrations.

- Basic setup audit exercise.

## Module 5 assets

Title: Build the Internal Content Operating System
Core chapters: 19–22, 29–33, 43–44, 47–48, 50–51, 56
Key visuals:

- One master asset → multiple derived assets flow.

- Weekly content operating cycle.

- Minimal software stack.

- Minimal gear system.

- AI workflow with human verification.

- “Tool trap” decision tree.

- Editing principles.

- Measurement scorecard.

- Improvement loop.

- 30-day and 90-day plan.

- Final Business Content System diagram.

# Phase 7: SureServer Deployment

Time required: 1 day once local site works
Deliverable: Private, live, tested course site.

## Step 7.1 — Create a staging subdomain

Do not deploy directly to your primary public domain page.

Create a subdomain such as:

text

camera.yourdomain.com

or:

text

training.yourdomain.com

Then create a staging subdomain:

text

staging-camera.yourdomain.com

Use:

text

staging-camera.yourdomain.com

for development/testing.

Use:

text

camera.yourdomain.com

for the actual instructor presentation environment.

## Recommended separation

| Environment | Purpose | Who sees it |
| --- | --- | --- |
| Localhost | Development and troubleshooting | You only |
| Staging subdomain | Browser/device/Zoom testing | You and selected testers |
| Live private subdomain | Actual cohort presentation | You, via Zoom share; optionally students for resources |
| Public marketing page | Enrollment and offer details | Prospects |

## Step 7.2 — Deployment procedure

Before every deployment:

- Verify the local version works.

- Commit the version to Git.

- ZIP the local project.

- Upload the ZIP archive to Google Drive Release folder.

- Record version and date in the Asset Register.

- Upload only the release files to staging.

- Test staging in Chrome and Edge.

- Test the presenter route.

- Test notes are hidden from audience route.

- Test direct URLs.

- Test keyboard navigation.

- Test the backup PDF.

- Only then upload to the live private site.

## Server release folder

On the server, preserve release archives outside the public web root if possible:

text

/home/youraccount/backups/camera-live/

In public HTML, deploy only the currently approved version.

If you need to restore, cPanel allows downloading and restoring account or partial backups; preserve your own copies rather than assuming the host’s backups are enough. Full cPanel backups are not automatically restorable by the account user in all cases, while partial backups can be restored through the appropriate cPanel interface.

## Step 7.3 — Basic server security checklist

- HTTPS enabled.

- Staging site password-protected.

- Presenter directory password-protected.

- noindex, nofollow meta tag on staging/presenter pages.

- robots.txt blocks staging and presenter routes.

- No credentials in public code.

- No debug error messages shown publicly.

- File-directory browsing disabled if your host supports it.

- No public link to presenter pages.

- Strong unique hosting password.

- Two-factor authentication enabled on hosting, Google, Zoom, and payment tools where available.

- Full site ZIP backup exists in Drive and locally before each major deployment.

## Simple robots rule

text

User-agent: *

Disallow: /presenter/

Disallow: /staging/

Disallow: /notes/

This is not security by itself. It only asks search engines not to crawl these routes. Password protection is the actual protective layer.

# Phase 8: Zoom Presentation Operating Procedure

Time required: 2–3 test sessions before the first cohort
Deliverable: A repeatable live teaching method with no accidental script exposure.

## Pre-course Zoom setup

Create one recurring Zoom Meeting series, or five scheduled meetings.

Recommended settings:

- Registration required.

- Waiting room enabled.

- Passcode enabled.

- Only authenticated users if that will not create too much friction for attendees.

- Screen sharing allowed for host only by default.

- Chat enabled.

- Recording enabled to cloud or local storage according to your plan and storage capacity.

- Auto-save chat if useful.

- Participants renamed to real names where possible.

- Closed captions enabled if available.

- Disable “join before host.”

- Disable file transfer unless you need it.

- Set co-hosts only for trusted people.

- Keep participant annotation disabled unless intentionally used.

## The night-before checklist

- Open the exact live module route.

- Confirm speaker notes work.

- Confirm the current deployed version matches the approved release.

- Open local offline site backup.

- Open PDF backup.

- Open workbook PDF.

- Open workbook Google Doc.

- Open Zoom meeting.

- Confirm your webcam, microphone, and speaker selection.

- Confirm screen-share window is correct.

- Disable desktop notifications.

- Close private emails, bank pages, messages, unrelated browser tabs, and file folders.

- Put phone on Do Not Disturb.

- Keep charger plugged in.

- Test internet.

- Prepare a hotspot backup if available.

- Print or open your one-page Instructor Run Sheet.

- Confirm the participant roster.

- Confirm any links you will paste into chat.

- Test recording.

- Create a clean desktop background if you might accidentally share your screen.

## The 30-minute-before checklist

- Restart laptop.

- Connect laptop power.

- Close unnecessary applications.

- Launch Zoom.

- Open the audience presentation site in Chrome.

- Open presenter notes in Edge or a second Chrome profile.

- Open local backup site in a separate browser tab.

- Open backup PDF in a separate application.

- Open Google Doc master script only if needed.

- Set browser zoom to the tested level.

- Put audience route in its own window.

- Put presenter route in a separate private window.

- Join Zoom as host.

- Start local recording test.

- Confirm your camera framing.

- Confirm your audio levels.

- Confirm the site starts on the proper opening scene.

## How to share safely

## Two-monitor setup

- Put your audience presentation window on Monitor 2.

- Put your presenter notes, Zoom controls, and script on Monitor 1.

- In Zoom, click Share.

- Choose the application window on Monitor 2—not “Entire Screen.”

- Confirm the green share indicator.

- Ask a test attendee or join from a second device to verify what is visible.

- Start teaching.

## One-monitor setup

- Open the audience teaching site in a normal browser window.

- Keep presenter notes in a different browser window behind it.

- Start Zoom.

- Click Share.

- Choose the specific browser window that contains the audience teaching site.

- Do not choose the full desktop.

- Begin the presentation in that shared window.

- Use keyboard navigation while the audience site retains focus.

- Check Zoom’s floating screen-share bar does not expose private content.

- If you need notes, use Alt + Tab carefully, but confirm Zoom is still sharing only the chosen audience window.

Zoom supports sharing a specific application window instead of the entire desktop, which is the key safeguard for keeping presenter notes and other private windows hidden.

## What students should see

They should see only:

- Your webcam when you choose to be on camera.

- The shared audience-facing teaching site.

- Purposeful exercises.

- Workbook page references.

- Selected demonstrations.

- Controlled screen captures or videos.

- Links you intentionally share.

They should not see:

- Your presenter script.

- Your speaker notes.

- Your Google Drive.

- Your email.

- Your local folders.

- Your LLM prompts.

- Your account credentials.

- Your Zoom host controls.

- Your browser tabs.

- Your raw source code.

## If you accidentally expose something

- Stop sharing immediately.

- Switch to camera view or blackout scene.

- Close or move the exposed content.

- Resume sharing only the correct application window.

- Do not panic or over-explain.

- Say: “I’m switching back to the teaching view.”

- Continue.

# Phase 9: Build Backup and Recovery Systems

Time required: Set up once, follow daily
Deliverable: Your work survives a laptop failure, hosting issue, mistaken upload, or bad code revision.

Use the 3-2-1 backup principle:

- Keep at least 3 copies.

- Store them on at least 2 different media/services.

- Keep at least 1 copy off-site.

## Your CAMERA backup model

| Copy | Location | What It Protects |
| --- | --- | --- |
| Working copy | Local laptop project folder | Daily development |
| Code history | Local Git repository | Every code change and rollback |
| Cloud document source | Google Drive | Scripts, workbook, asset register, source visuals, releases |
| Server copy | SureServer staging/live deployment | Actual delivery environment |
| Release archive | Google Drive + local ZIP | A complete restore point before/after every deployment |
| Optional additional copy | External USB drive or external SSD | Laptop failure and local-access emergency |

## Daily backup routine

At the end of every work session:

- Save all Google Docs and Sheets.

- Name important Google Doc revisions:

  - Session 1 Script — Pre-Review

  - Session 1 Script — Approved v1.0

  - Module 1 Workbook — Approved v1.0

- Commit code in Git.

- ZIP the project folder.

- Upload the ZIP to Google Drive.

- Update the Asset Register.

- Update the Change Log if the master curriculum changed.

- Write a short daily note:

  - What was completed.

  - What was changed.

  - What is next.

  - What is blocked.

Create a Google Doc:

text

CAMERA_V1_BUILD_LOG

Use this daily format:

text

DATE:

WORK SESSION:

COMPLETED:

FILES CREATED OR CHANGED:

DEPLOYMENTS:

TESTS RUN:

PROBLEMS FOUND:

NEXT BUILD TASK:

BACKUP CONFIRMED:

## Major-release procedure

Before any major live or staging deployment:

- Create a ZIP archive.

- Upload it to Drive.

- Label it RELEASE_CANDIDATE.

- Test it locally.

- Deploy to staging.

- Test on staging.

- Create a second ZIP archive labeled DEPLOYED.

- Upload it to Drive.

- Record the server route and version in the Asset Register.

- Do not overwrite your previous release archive.

Google Drive allows you to review and restore revision history for native documents. For key milestone files, explicitly label or preserve the approved version so it is not lost among routine edits.

# Phase 10: Sales, Scheduling, and Student Operations

Time required: Start in parallel during Week 2
Deliverable: A cohort scheduled while you complete the build.

Do not wait until all five modules are perfect to begin filling the room.

## Step 10.1 — Set the course start date

Set the first session about three to four weeks out.

Example timing:

| Week | Build / Sales Objective |
| --- | --- |
| Week 1 | Freeze offer, build Module 1, create landing page, set dates |
| Week 2 | Build Modules 2–3; begin direct invitations, emails, and audit calls |
| Week 3 | Build Modules 4–5; complete Zoom rehearsal; close enrollment |
| Week 4 | Deliver Session 1; finish refinements based on student intake |
| Weeks 5–8 | Deliver remaining sessions; collect feedback and testimonials |

If revenue urgency is severe, you can announce the program after Module 1 and the landing page exist, provided you have a fixed session structure and have honestly described the course as a live founding cohort.

## Step 10.2 — Build the minimum sales assets

Create:

text

09_MARKETING_AND_SALES/

├── CAMERA_V1_Landing_Page_Copy

├── CAMERA_V1_Offer_One_Sheet

├── CAMERA_V1_Founding_Cohort_FAQ

├── CAMERA_V1_Email_Invitation

├── CAMERA_V1_LinkedIn_DM

├── CAMERA_V1_Authority_Audit_Call_Script

├── CAMERA_V1_Payment_Instructions

└── CAMERA_V1_Enrollment_Confirmation

## Landing page must include

- What CAMERA is.

- Who it is for.

- Who it is not for.

- The business outcome.

- Five-session curriculum.

- Included materials.

- Dates and times.

- Founding price.

- Limited-seat statement.

- Refund/cancellation policy.

- What students need to bring.

- Technical requirements.

- Registration/payment button or instructions.

- Your professional background and why you are qualified to teach it.

- Clear distinction: CAMERA is education and implementation training, not agency video-production services and not the LEGAiSEE Business Archaeology service.

## Enrollment prompt for an LLM

text

Write a high-value, direct landing page for a live virtual business training program.

Program:

CAMERA™ Authority Media Training: Internal Content Capability Intensive

Audience:

Business owners, founders, professionals, spokespersons, and small content teams.

Core problem:

They keep paying agencies and production houses for content because they lack an

internal system, trained spokespersons, a practical setup, and a repeatable workflow.

Core outcome:

Participants create a practical internal business-content system: authority,

audience, content strategy, hooks, scripts, setup plan, gear/software plan,

workflow, AI process, 30-day calendar, and 90-day implementation plan.

Format:

Five live Zoom sessions, two hours each, with workbook, home-study readings,

templates, guides, and implementation assignments.

Tone:

Premium professional education. Direct, credible, specific, no hype.

Do not promise revenue, virality, guaranteed leads, or business outcomes.

Do not use generic AI marketing language.

Output sections:

1. Hero

2. Problem

3. What CAMERA is

4. Who it is for

5. Who it is not for

6. What students will build

7. Five-session curriculum

8. Included materials

9. Founding cohort details

10. Instructor credibility

11. FAQ

12. Registration CTA

## Step 10.3 — Student intake form

Create a Google Form:

text

CAMERA_V1_FOUNDING_COHORT_STUDENT_INTAKE

Ask:

- Name.

- Business name.

- Role.

- Website.

- Industry.

- Main product/service.

- Current content channels.

- Current content frequency.

- Current on-camera spokesperson, if any.

- Current equipment.

- Current software.

- Biggest content problem.

- Main business outcome desired from content.

- Why they enrolled.

- What they hope to have completed by the end.

- Permission to use anonymous, de-identified examples in class.

- Accessibility needs.

- Agreement to course terms and no-sharing policy.

Use their answers to tailor examples and identify likely questions before Session 1.

# Phase 11: Master LLM Workflow

Use the following sequence for every module. This is your repeatable production line.

Master Chapter→Live Selection→Presenter Script→Workbook→Scene Map→Site Code→Presenter Notes→QA→Deploy

Master Chapter→Live Selection→Presenter Script→Workbook→Scene Map→Site Code→Presenter Notes→QA→Deploy

## Step-by-step per lesson

## 1. Select source material

You decide the relevant textbook sections. Do not ask an LLM to decide the entire curriculum from scratch.

## 2. Create the presenter script

Use the presenter-script prompt above.

## 3. Review manually

Check:

- Does it sound like you?

- Does it preserve the master-book meaning?

- Does it include your practical judgment?

- Is it too generic?

- Does it over-explain?

- Does it contain claims you cannot support?

- Does it tell students exactly what to do?

- Is it teachable in the time available?

## 4. Generate workbook pages

Use the workbook prompt above.

## 5. Create a scene map

Prompt:

text

Turn the approved presenter script below into a scene map for a browser-based

live teaching presentation.

Do not write code yet.

For each scene provide:

- Scene ID

- Scene title

- Target duration

- Teaching objective

- On-screen copy, maximum 30–45 words unless it is an exercise

- Recommended visual component

- Required visual asset

- Workbook page reference

- Whether the scene needs a progressive reveal

- Speaker-note objective

- Transition to the next scene

Constraints:

- One teaching idea per scene.

- Avoid bullet-heavy pages.

- Prefer diagrams, comparisons, visual examples, annotated frames, and process flows.

- Build for Zoom screen sharing at normal laptop resolution.

- Do not use generic stock imagery as the default.

- Do not produce more scenes than necessary.

## 6. Approve on-screen copy

Edit it yourself. On-screen text should be concise. Your voice handles the full explanation.

## 7. Generate code

Use the scene-code prompt.

## 8. Generate presenter notes

Use the presenter-note prompt.

## 9. Test locally

Use the QA checklist.

## 10. Deploy only after approval

Release to staging, then live.

# Phase 12: Quality Assurance Checklist

Create:

text

CAMERA_V1_TEACHING_SITE_QA_CHECKLIST

Run it for every module.

## Content QA

- Teaching objective is clear.

- Presenter script matches the Master Textbook.

- Live material does not contradict the Master TOC.

- No unsupported claims, statistics, or invented case studies.

- No accidental legal, tax, medical, financial, or compliance advice.

- Exercises result in a usable business artifact.

- Homework advances implementation.

- Workbook references are correct.

- The session fits into two hours.

- Important concepts are repeated in recap or exercise form.

## Visual QA

- Every scene has one clear purpose.

- Large text is readable at Zoom screen-share size.

- Color contrast is adequate.

- Images have meaning; no decorative filler.

- Diagrams are understandable in under 10 seconds.

- No text runs off screen.

- No overly dense visual page.

- Progressive reveals work in correct order.

- Animations are restrained.

- Reduced-motion fallback exists.

- Alt text or meaningful text alternatives exist where appropriate.

The prefers-reduced-motion CSS media feature lets a site adapt when a user has requested reduced non-essential animation at the operating-system level.

## Technical QA

- Audience route loads.

- Presenter route loads only after authentication.

- Presenter notes do not appear on audience pages.

- Keyboard navigation works.

- Browser refresh preserves a reasonable state or route.

- Scene IDs are correct.

- No browser console errors.

- Links work.

- Full-screen works.

- Blackout works.

- Timer works.

- All images load over HTTPS.

- Desktop Chrome test passes.

- Desktop Edge test passes.

- Zoom screen-share test passes.

- Local offline backup works.

- PDF backup opens.

## Instructor QA

- The script is visible only to the instructor.

- You know the session objective.

- You can navigate forward/backward without looking.

- You know the exercise timing.

- You know the homework assignment.

- You know the fallback if a demo fails.

- You have a backup visual/PDF.

- You have the student roster and intake summaries.

- You have a one-page run sheet.

# Final Operating Recommendation

Build your first CAMERA live-teaching site as a private instructor tool, not a public self-guided course platform. The goal is a polished, differentiated Zoom classroom that you can sell quickly, deliver confidently, and improve from real student feedback.

Your minimum viable launch sequence is:

- Freeze the master structure.

- Define the five-session founding cohort.

- Create the offer and set the start date.

- Build the Drive, Git, file, and asset-control system.

- Build Module 1 fully.

- Launch enrollment.

- Build Modules 2–5 using the same system.

- Test presentation mechanics and hidden presenter notes.

- Deploy the private teaching site to SureServer.

- Deliver the cohort.

- Use recordings, questions, student work, and testimonials to build the full self-guided CAMERA master course.

The key discipline is this:

Do not let the desire for a perfect 75-chapter system delay the first paid cohort. Build the first five-session experience to a professional standard, sell it, teach it, document what happens, and let the real cohort become the field test that improves every later version.

What tools handle payment and registration for the founding cohort

How should the five live session curriculum be structured week by week

What specific backup system protects the teaching materials and server site

How do I configure Zoom to support interactive multi-person teaching securely

What is the exact folder structure and tech stack for the presenter site

# Gemini

# Conversation with Gemini

I am working on a course to sell to businesses who would like to take their content marketing internal and quit paying production houses and agencies to do it. I currently have a 58 Chapter Master Textbook and im presently working on the accompanying workbook. Once the workbook is complete, i want to take the Textbook and whittle it down to something that can be presented Live via zoom/virtual class. The goal of the zoom/virtual class is to add value by my 30 yr career of knowledge in the video production, broadcast and marketing fields. also for a way for me to make income quickly as i am currently unemployed. id like to price the zoom fair to atendeed for business knowledge but also a high value expertise/expert from my end maximizing proffit margin for myself per attendee. So.... I need a workflow to 1. whittle down a 58 chapter textbook to a 10-12 hour max - several day educational course. 2. Write the presenter script from that result. 3. A hopefully FREE first AI tool that could read the presenter script and or textbook and create a HIGH QUALITY/NON-Power Point LOOKING slide deck, with animations that presents as high dollar/quality. Give me a list of best fit options/pricing etc for different WORKFLOWS to accomplish my full task list. Along with the whittled down zoom version i want to create, Include Course Creation/Hosting options for a self/buyer guided FULL MASTER TEXTBOOK 58 Chapter end to end course. This would need security logins, anti-piracy theft of my course, auto pay/login-for buyer, my costs, etc. Present all responses in a properly formatted doc for copy/paste into google docs for my future reference.

I will now generate a comprehensive guide and workflow document containing the curriculum reduction strategy, scriptwriting process, AI slide deck tools, and course hosting/security options for your business video production course.

Course Creation and Launch Blueprint

# Comprehensive Course Creation, Curriculum Reduction, and Hosting Blueprint

## Executive Summary

This document outlines a step-by-step workflow to transform your 58-chapter master textbook on internalizing video content marketing into a high-ticket, multi-day live Zoom masterclass (10-12 hours total) for quick revenue generation. It also details the technology stack, free AI presentation tools, and secure hosting infrastructure required to package your full 58-chapter textbook into a self-paced, premium digital product protected against piracy.

## Phase 1: Curriculum Reduction Workflow (58 Chapters to 10-12 Hours)

To condense 58 chapters into a high-impact, 10-to-12-hour live virtual workshop that justifies premium B2B pricing, you must move from exhaustive theory to actionable operational frameworks.

### 1. The Consolidation Framework (The "Pillars" Method)

Group your 58 chapters into 4 distinct modules (representing 4 half-day sessions of 3 hours each, totaling 12 hours):

- Module 1: Strategy, Team Setup, and In-House Mindset (3 Hours)

  - Core focus: Eliminating agency reliance, defining the internal video mandate, budgeting hardware/software vs. outsourcing, and scoping lean internal teams.

- Module 2: Pre-Production & Studio Architecture (3 Hours)

  - Core focus: Building a permanent or modular in-office studio, lighting fundamentals for non-lighting experts, audio capture secrets (the most critical broadcast element), and scripting/formatting repeatable content series.

- Module 3: Production Execution & Broadcast Mastery (3 Hours)

  - Core focus: Camera operations (smartphones vs. mirrorless/cinema lines), teleprompter workflows, multi-cam setups, and directing on-camera talent who have zero experience.

- Module 4: Post-Production Pipeline & Distribution (3 Hours)

  - Core focus: Fast-turnaround editing systems, asset management, multi-platform repurposing (short-form to long-form), and performance analytics.

### 2. The Whittling Execution Steps

- Chapter Audit: Go through your table of contents and tag every chapter: Must Teach Live (Foundational/Transformational) vs. Reference Only (Workbook/Homework). Roughly 20-25% of chapters should be core live material; the remaining 75% become deep-dive reading and templates in your workbook.

- The 80/20 Rule Implementation: Focus live teaching strictly on what saves businesses money and prevents costly equipment mistakes. Leave technical deep-dives (e.g., advanced color grading or audio mastering) to workbook appendices.

## Phase 2: Presenter Scriptwriting Workflow

Writing a script for a 12-hour professional masterclass requires a modular structure that blends your 30 years of broadcast authority with high-engagement delivery techniques.

### Structure of a Script Segment (Per Module)

- The Hook & Cost Reality Check (5 Mins): Open with real-world industry examples of what agencies charge versus what in-house production costs. Leverage your 30 years of broadcast insight.

- The Framework/Core Lesson (45 Mins): Direct instruction supported by visual aids.

- The Live Case Study / Teardown (30 Mins): Analyze an actual piece of corporate content (good vs. bad) live on screen.

- Interactive Q&A / Hot Seat (40 Mins): Direct attendee engagement to maximize perceived value and address specific business bottlenecks.

### AI-Assisted Scriptwriting Prompt Workflow

Feed your textbook chapters into an AI model (like ChatGPT, Claude, or Gemini) using this exact prompt format:

"Act as an executive producer and senior broadcast coach with 30 years of experience. Using the provided text from Chapters [X, Y, Z], write a live presenter script for a high-end B2B masterclass. Tone: Authoritative, pragmatic, no-nonsense, empowering. Include verbal signposts, interactive engagement moments, and notes on where to show specific workbook assets."

## Phase 3: AI Presentation Design Tools (High-Value, Non-PowerPoint Look)

To command high-ticket B2B pricing, your slides cannot look like generic corporate PowerPoint templates. They need cinematic, modern, high-production aesthetic styling.

### Best Free / Freemium AI Presentation Tools

- Gamma.app (Freemium / Best Overall)

  - What it does: Generates stunning, modern, web-native layouts, cards, and visual frameworks automatically from raw text prompts or imported documents.

  - Free Tier: Generates complete decks with AI credits, clean typography, dynamic layouts, and modern visual cards. Avoids the boring PowerPoint box look entirely.

  - Export: Can be exported to PDF or PowerPoint if needed, but looks best presented directly via web browser.

- SlidesGPT / Tome.app (Freemium)

  - What it does: Builds narrative-driven slide decks complete with imagery placeholders and structured layouts based on script inputs.

  - Free Tier: Offers trial generations and basic workspace features.

- Canva (Magic Design Presentation - Freemium)

  - What it does: Feed your outline or script into Canva's Magic Design, and it instantly builds a custom-themed presentation using premium graphic templates.

  - Free Tier: Generates presentations using thousands of free designer templates; highly customizable.

## Phase 4: Course Creation, Hosting, & Security Options (Full 58-Chapter Master Textbook Course)

For your self-paced, buyer-guided 58-chapter course, you need a robust digital hosting platform that provides automated checkout, member authentication, and protection against content piracy.

### Top LMS / Hosting Platforms & Cost Structures

| Platform | Best For | Security & Anti-Piracy Features | Pricing & Costs |
| --- | --- | --- | --- |
| Kajabi | All-in-one marketing, payments, and course delivery. | Basic password protection, digital watermarking options, limits concurrent logins per account. | Starts around $149 - $199/month. Zero transaction fees on higher plans. |
| Teachable | Clean course UI and flexible pricing tiers. | Basic student encryption, compliance tracking, custom user roles. | Free tier (with high transaction fees) up to $59-$119/month for professional features. |
| Skool | Community-first hybrid courses combined with structured modules. | Moderated access, clean member lists, login tracking. | Flat $99/month flat fee. |
| Thinkific | Deep customization and secure video hosting. | Advanced DRM (Digital Rights Management) options, encrypted video streaming (prevents browser extensions from downloading raw MP4 files), watermarking. | Free basic plan; paid plans range from $49 - $149/month. |

### Anti-Piracy & Security Best Practices

- Encrypted Video Streaming: Never host raw video files on open platforms like standard YouTube or unprotected storage. Use platform-native secure players (like Thinkific's integrated Wistia/Vimeo enterprise secure embeds) that disable right-click downloads and block inspection tools.

- Dynamic User Watermarking: Implement email/IP watermarking on sensitive PDF textbooks or video streams so that if a user screen-records and leaks your content, their user ID or email is visibly burned into the frame.

- Concurrent Login Restrictions: Set platform limits so a single user account cannot stream content across 5 different IP addresses simultaneously (preventing password sharing among entire corporate teams).

## Recommended Launch Roadmap for Immediate Revenue

- Step 1 (Immediate Cash Flow): Use your outline to run a Live Zoom Beta Cohort over 4 half-days. Price it as an exclusive "Founding Member Executive Intensive." Sell directly via Stripe or a simple landing page to avoid complex platform setup costs.

- Step 2 (Productization): Record the live Zoom sessions. Take the polished recordings, combine them with your finalized workbook and the 58-chapter textbook, and upload them to a secure platform like Thinkific or Kajabi to sell as an automated, self-paced master program.

Edit directly or with Gemini

Click anywhere to type and edit directly, or select text to prompt Gemini for changes.

CAMERA™ V1 — MASTER TABLE OF CONTENTS

CAMERA™ Authority Media Training System

Purpose: Teach businesses, business owners, founders, professionals, spokespersons, and content teams how to plan, create, present, produce, edit, publish, and sustain their own effective video and content marketing in the modern AI-enabled media environment.

V1 Position: Education and implementation training. CAMERA does not provide the Business Archaeology service of LEGAiSEE. Students learn how to build and operate their own content capability.

Primary Delivery: Live virtual instruction, with optional in-person delivery.

Core Student Outcome: By completion, the student should understand what their business actually needs, know how to create it themselves, know what equipment and software are appropriate for their situation, be capable of appearing professionally on camera, understand how to turn expertise into useful content, and possess a repeatable content-production workflow that can be sustained after the course.

PART I — CAMERA SYSTEM FOUNDATION

Chapter 1 — What CAMERA Is

1.1 The Purpose of CAMERA

1.2 What CAMERA Teaches

1.3 What CAMERA Does Not Teach

1.4 CAMERA vs. Traditional Video Production

1.5 CAMERA vs. Hiring a Production Company

1.6 CAMERA vs. Hiring a Social Media Agency

1.7 CAMERA as an Internal Business Capability

1.8 The Modern Content Environment

1.9 The Impact of Artificial Intelligence and LLMs

1.10 Human Expertise + Media Skills + AI Assistance

1.11 The “Start With What You Have” Principle

1.12 The CAMERA Completion Standard

PART II — THE CAMERA OPERATING MODEL

Chapter 2 — The CAMERA Framework

2.1 The Six Dimensions

2.2 C — Character

2.3 A — Audience

2.4 M — Monetization

2.5 E — Engagement

2.6 R — Repurposing

2.7 A — AI Acceleration

2.8 How the Six Dimensions Connect

2.9 CAMERA as a Continuous Operating System

2.10 The Difference Between Strategy and Execution

2.11 The Difference Between Content and Marketing

2.12 The Difference Between Visibility and Authority

PART III — BUSINESS CONTENT DIAGNOSIS

Chapter 3 — Determine What Your Business Actually Needs

3.1 Stop Starting With the Camera

3.2 Start With the Business

3.3 The Content Requirement Assessment

3.4 Business Type and Content Requirements

3.5 Local Consumer Businesses

3.6 Professional Services

3.7 B2B Businesses

3.8 Founder-Led Businesses

3.9 Sales-Driven Businesses

3.10 Expert and Practitioner Businesses

3.11 Personal Brands

3.12 Spokesperson-Based Businesses

3.13 Businesses With Multiple Departmental Voices

3.14 Businesses With No Natural On-Camera Personality

3.15 One-Person Content Operations

3.16 Small Internal Content Teams

3.17 Enterprise Content Teams

3.18 Choosing the Appropriate Content Model

3.19 The Minimum Viable Content Operation

3.20 The Content Capability Ladder

PART IV — C: CHARACTER

Chapter 4 — Character: Who Is On Camera?

4.1 Character vs. Persona

4.2 Authentic Authority

4.3 The Business Owner as Authority

4.4 The Founder as the Face of the Company

4.5 The Professional Practitioner as Authority

4.6 The Employee as Spokesperson

4.7 Multiple Spokespeople

4.8 Personal Brand vs. Corporate Brand

4.9 Defining the On-Camera Character

4.10 Identifying Existing Professional Authority

4.11 Experience as Content

4.12 Knowledge as Content

4.13 Personality Without Performance

4.14 Credibility Without Corporate Stiffness

4.15 Building a Consistent On-Camera Identity

4.16 Character Exercise

4.17 Character Worksheet

4.18 Character Implementation Assignment

Chapter 5 — On-Camera Presence

5.1 Why People Look Different on Camera

5.2 Camera Awareness

5.3 Eye Line

5.4 Posture

5.5 Body Position

5.6 Facial Expression

5.7 Hand Movement

5.8 Natural Movement

5.9 Stillness

5.10 Energy

5.11 Confidence

5.12 Authority

5.13 Warmth

5.14 Conversational Presence

5.15 Avoiding “Talking Head” Syndrome

5.16 Looking Into the Lens

5.17 Looking at a Screen

5.18 Camera Height

5.19 Camera Distance

5.20 Framing

5.21 Headroom

5.22 Background Relationship

5.23 On-Camera Presence Exercise

5.24 Self-Assessment

PART V — A: AUDIENCE

Chapter 6 — Understanding the Person Watching

6.1 Audience Is More Than Demographics

6.2 Who Are You Actually Talking To?

6.3 Buyer vs. Viewer

6.4 Decision-Maker vs. Influencer

6.5 Audience Intent

6.6 Problems

6.7 Questions

6.8 Fears

6.9 Desires

6.10 Objections

6.11 Misconceptions

6.12 Existing Knowledge

6.13 Buying Readiness

6.14 Audience Language

6.15 Speaking to the Audience’s Current State

6.16 Audience Exercise

6.17 Audience Profile Worksheet

Chapter 7 — Content That Serves the Audience

7.1 Education vs. Promotion

7.2 Information vs. Insight

7.3 Solving Problems

7.4 Answering Questions

7.5 Demonstrating Expertise

7.6 Teaching Without Giving Away the Business

7.7 Building Trust Through Useful Information

7.8 Stories as Teaching Devices

7.9 Proof

7.10 Case Studies

7.11 Demonstrations

7.12 FAQs

7.13 Myth-Busting

7.14 Behind-the-Scenes Content

7.15 Audience Content Exercise

PART VI — M: MONETIZATION

Chapter 8 — Connecting Content to the Business

8.1 Content Is Not the Business

8.2 What Are You Actually Selling?

8.3 Mapping Content to Offers

8.4 Awareness Content

8.5 Consideration Content

8.6 Decision Content

8.7 Authority Content

8.8 Lead Generation Content

8.9 Sales Support Content

8.10 Customer Education Content

8.11 Retention Content

8.12 Recruiting Content

8.13 Employer Brand Content

8.14 Content and the Customer Journey

8.15 Calls to Action

8.16 Soft vs. Direct Calls to Action

8.17 Designing the Next Step

8.18 Content-to-Revenue Mapping Exercise

Chapter 9 — Building the Business Content Strategy

9.1 Content Pillars

9.2 Authority Pillars

9.3 Product/Service Pillars

9.4 Customer Problem Pillars

9.5 Proof Pillars

9.6 Story Pillars

9.7 Brand Pillars

9.8 Promotional Pillars

9.9 Evergreen vs. Timely Content

9.10 Short-Form vs. Long-Form

9.11 Establishing Content Priorities

9.12 Determining Posting Frequency

9.13 Determining Production Capacity

9.14 Building a Sustainable Strategy

9.15 30-Day Content Strategy Exercise

PART VII — E: ENGAGEMENT

Chapter 10 — Understanding Attention

10.1 The Economics of Attention

10.2 Why People Stop Scrolling

10.3 The First Frame

10.4 The First Sentence

10.5 The First Three Seconds

10.6 Relevance

10.7 Curiosity

10.8 Tension

10.9 Specificity

10.10 Stakes

10.11 Pattern Interrupts

10.12 The Difference Between Clickbait and a Useful Hook

Chapter 11 — Hook Construction

11.1 The Problem Hook

11.2 The Question Hook

11.3 The Statement Hook

11.4 The Contrarian Hook

11.5 The Story Hook

11.6 The Demonstration Hook

11.7 The Mistake Hook

11.8 The “You Are Doing This Wrong” Structure

11.9 The “Before You Do X” Structure

11.10 The Authority Hook

11.11 The Curiosity Gap

11.12 Hook Testing

11.13 Hook Workshop

11.14 Hook Worksheet

Chapter 12 — Retention and Delivery

12.1 Why People Leave

12.2 Information Density

12.3 Pacing

12.4 Pauses

12.5 Sentence Length

12.6 Visual Change

12.7 B-Roll

12.8 Text Overlays

12.9 Demonstrations

12.10 Stories

12.11 Open Loops

12.12 Payoffs

12.13 Structuring an Argument

12.14 Ending Strongly

12.15 Retention Exercise

PART VIII — ON-CAMERA DELIVERY

Chapter 13 — Speaking Naturally

13.1 Memorization vs. Internalization

13.2 Word-for-Word Scripts

13.3 Bullet-Point Outlines

13.4 Conversational Delivery

13.5 Learning the Thought Instead of the Sentence

13.6 Reading Without Looking Like You Are Reading

13.7 Teleprompters

13.8 When to Use a Teleprompter

13.9 When Not to Use a Teleprompter

13.10 Recovering From a Missed Line

13.11 Restarting

13.12 Pausing

13.13 Editing Around Mistakes

13.14 Improvisation

13.15 Speaking From Experience

Chapter 14 — Voice, Rhythm and Authority

14.1 Vocal Presence

14.2 Volume

14.3 Pitch

14.4 Pace

14.5 Rhythm

14.6 Emphasis

14.7 Pausing

14.8 Breath

14.9 Eliminating Vocal Filler

14.10 Avoiding Monotone Delivery

14.11 Sounding Professional Without Sounding Scripted

14.12 Sounding Human

14.13 Voice Exercise

14.14 Delivery Self-Assessment

PART IX — CAMERA AND VISUAL FOUNDATIONS

Chapter 15 — The Camera

15.1 Phone vs. Webcam vs. Dedicated Camera

15.2 Why the Camera Is Not the Most Important Component

15.3 Resolution

15.4 Frame Rate

15.5 Exposure

15.6 White Balance

15.7 Focus

15.8 Lens Choice

15.9 Sensor Size

15.10 Front-Facing vs. Rear-Facing Phone Cameras

15.11 Horizontal vs. Vertical

15.12 16:9

15.13 9:16

15.14 1:1 and Other Formats

15.15 Camera Placement

15.16 Camera Height

15.17 Camera Distance

15.18 Framing for Different Platforms

15.19 Camera Setup Practical

PART X — LIGHTING

Chapter 16 — Making People Look Better

16.1 Why Lighting Matters

16.2 Quality of Light

16.3 Direction of Light

16.4 Size of Light Source

16.5 Natural Window Light

16.6 One-Light Setup

16.7 Two-Light Setup

16.8 Three-Point Lighting

16.9 Key Light

16.10 Fill Light

16.11 Backlight/Rim Light

16.12 Soft Light

16.13 Hard Light

16.14 Shadows

16.15 Color Temperature

16.16 Mixed Lighting

16.17 Practical Lights

16.18 Lighting Small Rooms

16.19 Lighting Offices

16.20 Lighting Retail/Business Locations

16.21 Lighting on a Budget

16.22 Lighting Troubleshooting

16.23 Lighting Practical

PART XI — BACKGROUND AND SET DESIGN

Chapter 17 — What the Camera Sees Behind You

17.1 Background as Communication

17.2 Intentional vs. Accidental Backgrounds

17.3 Depth

17.4 Separation

17.5 Clutter

17.6 Color

17.7 Branding

17.8 Office Environments

17.9 Professional Environments

17.10 Home Environments

17.11 Retail Environments

17.12 Clinical Environments

17.13 Workshop/Industrial Environments

17.14 Founder/Executive Backgrounds

17.15 Personal Brand Backgrounds

17.16 Virtual Backgrounds

17.17 Green Screen

17.18 Building a Repeatable Set

17.19 Background Practical

PART XII — AUDIO

Chapter 18 — Sound Is Half the Picture

18.1 Why Audio Matters More Than Camera Quality

18.2 Room Acoustics

18.3 Echo

18.4 Background Noise

18.5 Microphone Types

18.6 Built-In Phone Microphones

18.7 Wired Lavalier Microphones

18.8 Wireless Lavalier Systems

18.9 Shotgun Microphones

18.10 USB Microphones

18.11 XLR Microphones

18.12 Microphone Placement

18.13 Recording Levels

18.14 Clipping

18.15 Monitoring

18.16 Room Treatment

18.17 Audio Cleanup

18.18 Audio Troubleshooting

18.19 Audio Practical

PART XIII — R: REPURPOSING

Chapter 19 — One Idea, Multiple Assets

19.1 The Repurposing Principle

19.2 Stop Creating From Scratch

19.3 The Master Content Asset

19.4 Long-Form to Short-Form

19.5 Video to Text

19.6 Video to Email

19.7 Video to Blog

19.8 Video to Social Posts

19.9 Video to Sales Material

19.10 Video to Training Material

19.11 Video to FAQ Content

19.12 Video to Clips

19.13 Video to B-Roll Library

19.14 The 1-to-Many Content Model

19.15 Repurposing Exercise

Chapter 20 — Building the Content Production Workflow

20.1 Idea Capture

20.2 Research

20.3 Content Brief

20.4 Script

20.5 Recording

20.6 Ingest

20.7 Editing

20.8 Captioning

20.9 Review

20.10 Approval

20.11 Publishing

20.12 Distribution

20.13 Engagement

20.14 Measurement

20.15 Archiving

20.16 File Naming

20.17 Folder Structure

20.18 Backup

20.19 Batching

20.20 The Weekly Content Operating Cycle

20.21 Workflow Implementation Exercise

PART XIV — EDITING

Chapter 21 — Editing for the Modern Business

21.1 What Editing Actually Does

21.2 Cutting Dead Time

21.3 Removing Mistakes

21.4 Jump Cuts

21.5 Pacing

21.6 Captions

21.7 Text Overlays

21.8 Graphics

21.9 B-Roll

21.10 Music

21.11 Sound Effects

21.12 Transitions

21.13 What Not to Do

21.14 Keeping Editing Invisible

21.15 Editing for Authority

Chapter 22 — Editing Software

22.1 Choosing Software Based on Skill

22.2 Phone-First Editing

22.3 CapCut

22.4 Desktop Editing

22.5 Clipchamp

22.6 DaVinci Resolve

22.7 Adobe Premiere

22.8 Descript

22.9 Choosing One Primary Editor

22.10 Basic Editing Workflow

22.11 Captions Workflow

22.12 Export Workflow

22.13 Editing Practical

PART XV — PLATFORM MASTERY

Chapter 23 — YouTube

23.1 What YouTube Is Good For

23.2 Long-Form Authority

23.3 Shorts

23.4 Channel Positioning

23.5 Series Architecture

23.6 Titles

23.7 Thumbnails

23.8 Opening Structure

23.9 Retention

23.10 Calls to Action

23.11 YouTube Workflow

23.12 YouTube Practical

Chapter 24 — LinkedIn

24.1 Professional Authority

24.2 Founder Content

24.3 Expert Content

24.4 Video Posts

24.5 Text Posts

24.6 Document Posts

24.7 Personal vs. Company Pages

24.8 LinkedIn Thought Leadership

24.9 LinkedIn Engagement

24.10 LinkedIn Calls to Action

24.11 LinkedIn Workflow

Chapter 25 — Instagram

25.1 Reels

25.2 Stories

25.3 Carousels

25.4 Visual Authority

25.5 Short-Form Rhythm

25.6 Captions

25.7 Calls to Action

25.8 Direct Messages

25.9 Instagram Workflow

Chapter 26 — TikTok

26.1 TikTok Content Behavior

26.2 Opening Seconds

26.3 Pattern Interrupts

26.4 Educational Content

26.5 Personality

26.6 Comment Interaction

26.7 Search-Oriented Content

26.8 TikTok Workflow

Chapter 27 — Facebook

27.1 Local Business Content

27.2 Community Content

27.3 Reels

27.4 Groups

27.5 Business Pages

27.6 Customer Trust

27.7 Facebook Workflow

Chapter 28 — Other Distribution Channels

28.1 Email

28.2 Website

28.3 Landing Pages

28.4 Google Business Presence

28.5 Sales Presentations

28.6 Internal Communications

28.7 Customer Education

28.8 Choosing Channels Based on Business Need

PART XVI — A: AI ACCELERATION

Chapter 29 — AI in the Modern Content Workflow

29.1 What AI Is

29.2 What AI Is Not

29.3 AI as a Tool

29.4 AI Does Not Replace Expertise

29.5 Human Judgment

29.6 The AI-Assisted Content Workflow

29.7 Research Assistance

29.8 Idea Generation

29.9 Content Outlining

29.10 Script Drafting

29.11 Hook Development

29.12 Headline Development

29.13 Repurposing

29.14 Caption Creation

29.15 Transcription

29.16 Editing Assistance

29.17 Research Verification

29.18 Content Analysis

29.19 Performance Analysis

Chapter 30 — Working With LLMs

30.1 What an LLM Actually Does

30.2 Context

30.3 Prompting

30.4 Providing Source Material

30.5 Giving the AI a Job

30.6 Giving the AI Constraints

30.7 Iteration

30.8 Criticism and Revision

30.9 Fact Checking

30.10 Maintaining Personal Voice

30.11 Avoiding Generic AI Language

30.12 AI-Assisted Brainstorming

30.13 AI-Assisted Scripting

30.14 AI-Assisted Repurposing

30.15 Building Reusable Prompt Systems

30.16 Student AI Workflow Exercise

Chapter 31 — Avoiding the AI Tool Trap

31.1 The Ten-Subscription Problem

31.2 Tools vs. Workflow

31.3 Free Tools First

31.4 When a Paid Tool Is Justified

31.5 Subscriptions

31.6 Credits and Tokens

31.7 Model Selection

31.8 Avoiding Tool Chasing

31.9 Building a Small AI Stack

31.10 Evaluating New AI Tools

31.11 AI Tool Decision Worksheet

PART XVII — CONTENT CREATION PRACTICALS

Chapter 32 — Building a Video From Scratch

32.1 Select the Objective

32.2 Select the Audience

32.3 Select the Topic

32.4 Build the Hook

32.5 Build the Argument

32.6 Build the CTA

32.7 Write the Script

32.8 Prepare the Environment

32.9 Set the Camera

32.10 Set the Lighting

32.11 Set the Audio

32.12 Record

32.13 Review

32.14 Edit

32.15 Caption

32.16 Export

32.17 Publish

32.18 Measure

32.19 Practical Assignment

Chapter 33 — The 60-Second Authority Video

33.1 Selecting the Topic

33.2 Hook

33.3 Setup

33.4 Teaching

33.5 Proof

33.6 CTA

33.7 Recording Exercise

33.8 Editing Exercise

33.9 Peer Review

33.10 Instructor Review

Chapter 34 — The Long-Form Authority Piece

34.1 Choosing a Larger Topic

34.2 Research

34.3 Structure

34.4 Opening

34.5 Argument

34.6 Examples

34.7 Demonstration

34.8 Story

34.9 Conclusion

34.10 CTA

34.11 Recording

34.12 Editing

34.13 Repurposing

PART XVIII — CONTENT PRODUCTION FOR DIFFERENT BUSINESS MODELS

Chapter 35 — The Business Owner Model

35.1 Owner as Primary Authority

35.2 Owner-Led Content

35.3 Limited Time

35.4 Batch Production

35.5 Minimum Viable Weekly Schedule

35.6 Delegation

35.7 Owner Approval

35.8 Implementation Exercise

Chapter 36 — The Permanent Spokesperson Model

36.1 Selecting the Spokesperson

36.2 Training the Spokesperson

36.3 Content Responsibilities

36.4 Recurring Content Formats

36.5 Maintaining Consistency

36.6 Staff Participation

36.7 Salesperson-Generated Content

36.8 Departmental Content

36.9 Implementation Exercise

Chapter 37 — The Founder-Led Authority Model

37.1 Founder as Public Authority

37.2 Personal Brand

37.3 Corporate Brand Relationship

37.4 Thought Leadership

37.5 Founder Stories

37.6 Industry Commentary

37.7 Education

37.8 Interviews

37.9 Long-Form Content

37.10 Short-Form Content

37.11 Building the Founder Content Engine

Chapter 38 — The Personal Influencer Model

38.1 Personal Brand Architecture

38.2 Audience Relationship

38.3 Personality-Led Content

38.4 Platform Selection

38.5 Consistency

38.6 Monetization Models

38.7 Boundaries

38.8 Reputation

38.9 Privacy and Safety

38.10 Sustainable Production

PART XIX — ADVANCED PRODUCTION

Chapter 39 — B-Roll and Visual Storytelling

39.1 What B-Roll Does

39.2 Types of B-Roll

39.3 Business B-Roll

39.4 Product B-Roll

39.5 Service B-Roll

39.6 Environmental B-Roll

39.7 People at Work

39.8 Demonstration B-Roll

39.9 Shooting a B-Roll Library

39.10 B-Roll Shot List

Chapter 40 — Multi-Camera and Advanced Production

40.1 When Multiple Cameras Are Useful

40.2 Two-Camera Interviews

40.3 Multi-Angle Presentations

40.4 Camera Matching

40.5 Audio Synchronization

40.6 B-Roll Integration

40.7 Recording Longer Sessions

40.8 Production Planning

40.9 When Not to Overproduce

PART XX — CONTENT OPERATIONS

Chapter 41 — Building the Internal Content Department

41.1 Who Does What?

41.2 Owner

41.3 Spokesperson

41.4 Content Strategist

41.5 Writer

41.6 Camera Operator

41.7 Editor

41.8 Publisher

41.9 Community Manager

41.10 AI Assistance

41.11 One Person Wearing Multiple Roles

41.12 Small-Team Configuration

41.13 Larger-Team Configuration

41.14 Responsibility Matrix

Chapter 42 — Content Management

42.1 Content Calendar

42.2 Editorial Calendar

42.3 Production Calendar

42.4 Asset Library

42.5 Content Database

42.6 Script Library

42.7 B-Roll Library

42.8 Brand Assets

42.9 File Management

42.10 Backup

42.11 Version Control

42.12 Approval Process

PART XXI — MEASUREMENT AND IMPROVEMENT

Chapter 43 — Measuring What Matters

43.1 Vanity Metrics

43.2 Reach

43.3 Views

43.4 Watch Time

43.5 Retention

43.6 Engagement

43.7 Clicks

43.8 Leads

43.9 Conversations

43.10 Appointments

43.11 Sales

43.12 Customer Acquisition

43.13 Business-Specific KPIs

43.14 Choosing the Right Metrics

Chapter 44 — The Content Improvement Loop

44.1 Publish

44.2 Observe

44.3 Measure

44.4 Diagnose

44.5 Modify

44.6 Test

44.7 Repeat

44.8 A/B Testing Concepts

44.9 Hook Testing

44.10 Format Testing

44.11 Topic Testing

44.12 CTA Testing

44.13 Building a Learning Library

PART XXII — REPUTATION AND CRISIS

Chapter 45 — Protecting Authority

45.1 Public Mistakes

45.2 Incorrect Information

45.3 Misstatements

45.4 Negative Comments

45.5 Hostile Comments

45.6 Criticism

45.7 Customer Complaints

45.8 Viral Negative Content

45.9 When to Respond

45.10 When Not to Respond

45.11 Correction Protocol

45.12 Reputation-Sensitive Topics

45.13 Personal Boundaries

45.14 Crisis Response Exercise

PART XXIII — PROFESSIONAL PRACTICE

Chapter 46 — Legal, Ethical and Platform Considerations

46.1 Copyright

46.2 Music Licensing

46.3 Stock Media

46.4 Image Rights

46.5 Consent

46.6 Customer Privacy

46.7 Employee Privacy

46.8 Medical/Professional Content Considerations

46.9 Claims and Advertising

46.10 AI Disclosure Considerations

46.11 Platform Rules

46.12 Record Keeping

46.13 When to Obtain Professional Legal Advice

PART XXIV — GEAR SYSTEM

Chapter 47 — Gear Philosophy

47.1 Buy for the Problem

47.2 Don’t Buy for Status

47.3 Phone First

47.4 Audio First

47.5 Lighting Before Camera Upgrades

47.6 Buy Once vs. Upgrade Later

47.7 Used Equipment

47.8 Business Equipment vs. Creator Equipment

47.9 Matching Equipment to Content Requirements

Chapter 48 — Budget Gear Configurations

48.1 $0–$100 Setup

48.2 $100–$250 Setup

48.3 $250–$500 Setup

48.4 $500–$1,000 Setup

48.5 $1,000–$2,500 Setup

48.6 $2,500+ Professional Setup

48.7 Phone-Only Configuration

48.8 Laptop/Webcam Configuration

48.9 Home Studio Configuration

48.10 Office Configuration

48.11 Mobile Configuration

48.12 Interview Configuration

48.13 Multi-Camera Configuration

Chapter 49 — Gear Selection Guides

49.1 Phones

49.2 Cameras

49.3 Lenses

49.4 Tripods

49.5 Phone Mounts

49.6 Lighting

49.7 Light Modifiers

49.8 Microphones

49.9 Audio Interfaces

49.10 Headphones

49.11 Teleprompters

49.12 Backgrounds

49.13 Acoustic Treatment

49.14 Cables and Adapters

49.15 Storage

49.16 Backup

PART XXV — SOFTWARE SYSTEM

Chapter 50 — The Minimal Software Stack

50.1 Recording

50.2 Editing

50.3 Captions

50.4 Thumbnails

50.5 Storage

50.6 Scheduling

50.7 Analytics

50.8 AI

50.9 Communication

50.10 Choosing the Smallest Useful Stack

Chapter 51 — Software Workflows

51.1 Phone → Edit → Publish

51.2 Camera → Computer → Edit → Publish

51.3 Zoom → Recording → Edit → Repurpose

51.4 Long-Form → Shorts

51.5 Video → Transcript → AI → Content

51.6 Content Calendar → Production

51.7 Backup and Archive

PART XXVI — PRACTICAL WORKSHOPS

Chapter 52 — Workshop: Build Your First Setup

52.1 Equipment Assessment

52.2 Room Assessment

52.3 Camera Setup

52.4 Lighting Setup

52.5 Audio Setup

52.6 Background Setup

52.7 Test Recording

52.8 Troubleshooting

52.9 Final Setup Review

Chapter 53 — Workshop: Write Your First Five Videos

53.1 Select Five Topics

53.2 Define Audience

53.3 Define Objective

53.4 Write Hooks

53.5 Build Arguments

53.6 Add Proof

53.7 Add CTA

53.8 Create Scripts

53.9 Instructor Review

Chapter 54 — Workshop: Record Your First Videos

54.1 Preparation

54.2 Camera Check

54.3 Audio Check

54.4 Lighting Check

54.5 Delivery

54.6 Retakes

54.7 Reviewing Footage

54.8 Selecting Takes

54.9 Instructor Feedback

Chapter 55 — Workshop: Edit and Publish

55.1 Import

55.2 Organize

55.3 Cut

55.4 Caption

55.5 Add Supporting Visuals

55.6 Export

55.7 Upload

55.8 Metadata

55.9 CTA

55.10 Publish

55.11 Review Performance

PART XXVII — THE STUDENT IMPLEMENTATION PROJECT

Chapter 56 — Build Your Business Content System

56.1 Business Content Assessment

56.2 Character Definition

56.3 Audience Definition

56.4 Monetization Map

56.5 Content Pillars

56.6 Engagement System

56.7 Repurposing System

56.8 AI Workflow

56.9 Gear Configuration

56.10 Software Configuration

56.11 Production Workflow

56.12 Publishing Schedule

56.13 Measurement Plan

56.14 30-Day Implementation Plan

56.15 90-Day Growth Plan

PART XXVIII — COURSE COMPLETION

Chapter 57 — Final Practical Examination

57.1 Business Content Strategy

57.2 On-Camera Performance

57.3 Technical Setup

57.4 Content Construction

57.5 Editing

57.6 Publishing

57.7 Repurposing

57.8 AI Workflow

57.9 Troubleshooting

57.10 Final Instructor Review

Chapter 58 — CAMERA Certification

58.1 Completion Requirements

58.2 Practical Requirements

58.3 Project Requirements

58.4 Certificate Standards

58.5 Certificate Issuance

58.6 Student Completion Record

58.7 Continuing Education

Instructor manual????/?/

PART XXIX — CLIENT/STUDENT WORKBOOK

Workbook 1 — Student Orientation

1.1 Personal Goals

1.2 Business Goals

1.3 Current Content Situation

1.4 Current Equipment

1.5 Current Software

1.6 Current Skills

1.7 Current Obstacles

1.8 Desired Outcome

Workbook 2 — CAMERA Assessment

2.1 Business Assessment

2.2 Content Assessment

2.3 Audience Assessment

2.4 Production Assessment

2.5 Technology Assessment

2.6 AI Assessment

2.7 Capability Gap

Workbook 3 — C: Character

3.1 Authority Inventory

3.2 Experience Inventory

3.3 Personality

3.4 Positioning

3.5 On-Camera Identity

Workbook 4 — A: Audience

4.1 Audience Definition

4.2 Buyer Psychology

4.3 Problems

4.4 Questions

4.5 Objections

4.6 Desired Outcomes

Workbook 5 — M: Monetization

5.1 Offers

5.2 Customer Journey

5.3 Content-to-Offer Map

5.4 CTA Library

5.5 Revenue Content Plan

Workbook 6 — E: Engagement

6.1 Hook Bank

6.2 Content Structures

6.3 Retention Checklist

6.4 CTA Practice

6.5 Video Self-Critique

Workbook 7 — Production Setup

7.1 Camera

7.2 Audio

7.3 Lighting

7.4 Background

7.5 Room

7.6 Software

7.7 Test Recording

7.8 Final Setup

Workbook 8 — R: Repurposing

8.1 Master Content Asset

8.2 Derivative Assets

8.3 Platform Map

8.4 Production Workflow

8.5 Content Calendar

Workbook 9 — A: AI Acceleration

9.1 Current AI Tools

9.2 AI Tasks

9.3 Prompt Construction

9.4 Voice and Style

9.5 Verification

9.6 AI Workflow

9.7 AI Tool Audit

Workbook 10 — 30-Day Implementation

10.1 Content Goals

10.2 Production Schedule

10.3 Publishing Schedule

10.4 Content Topics

10.5 Metrics

10.6 Weekly Review

10.7 Adjustments

PART XXX — GEAR AND RESOURCE HANDBOOK

Chapter 59 — Equipment Reference

59.1 Phone-First Gear

59.2 Entry-Level Gear

59.3 Intermediate Gear

59.4 Professional Gear

59.5 Audio Reference

59.6 Lighting Reference

59.7 Camera Reference

59.8 Support Equipment

59.9 Studio Equipment

59.10 Equipment Decision Matrix

Chapter 60 — Software Reference

60.1 Free Software

60.2 Freemium Software

60.3 Paid Software

60.4 AI Tools

60.5 Editing Tools

60.6 Recording Tools

60.7 Captioning Tools

60.8 Storage Tools

60.9 Scheduling Tools

60.10 Analytics Tools

60.11 Recommended Minimal Stacks

PART XXXI — STUDENT QUICK-REFERENCE MANUAL

Chapter 61 — Pre-Production

61.1 Idea Checklist

61.2 Audience Checklist

61.3 Script Checklist

61.4 Equipment Checklist

61.5 Location Checklist

Chapter 62 — Pre-Recording

62.1 Camera

62.2 Framing

62.3 Lighting

62.4 Audio

62.5 Background

62.6 Appearance

62.7 Script

62.8 Test Recording

Chapter 63 — Recording

63.1 Start

63.2 Deliver

63.3 Recover

63.4 Retake

63.5 Finish

Chapter 64 — Editing

64.1 Import

64.2 Select

64.3 Cut

64.4 Caption

64.5 Enhance

64.6 Export

Chapter 65 — Publishing

65.1 Platform

65.2 Title

65.3 Description

65.4 Caption

65.5 Thumbnail

65.6 CTA

65.7 Publish

65.8 Measure

PART XXXII — INSTRUCTOR SYSTEM

Chapter 66 — Instructor Operating Manual

66.1 Instructor Role

66.2 Course Philosophy

66.3 Teaching Standards

66.4 Student Experience Standards

66.5 Class Preparation

66.6 Live Session Procedure

66.7 Demonstration Procedure

66.8 Exercise Procedure

66.9 Student Review Procedure

66.10 Feedback Standards

66.11 Assignment Management

66.12 Attendance

66.13 Completion Tracking

66.14 Certification

Chapter 67 — Instructor Lesson Plans

67.1 Session Objectives

67.2 Teaching Points

67.3 Demonstrations

67.4 Exercises

67.5 Discussion Questions

67.6 Practical Assignments

67.7 Instructor Prompter Script

67.8 Timing

67.9 Transition Notes

67.10 Troubleshooting

PART XXXIII — SLIDE SYSTEM

Chapter 68 — Client-Facing Presentation Deck

68.1 Slide Design Standards

68.2 Teaching Slides vs. Reference Slides

68.3 Visual Demonstrations

68.4 Examples

68.5 Diagrams

68.6 Exercises

68.7 Practical Demonstrations

68.8 Session Recaps

68.9 Assignment Slides

68.10 Completion Slides

Chapter 69 — Instructor Prompter System

69.1 Slide Number

69.2 Teaching Objective

69.3 Instructor Script

69.4 Demonstration Instructions

69.5 Questions to Ask

69.6 Expected Student Responses

69.7 Exercise Instructions

69.8 Timing

69.9 Transition to Next Slide

69.10 Instructor Notes

PART XXXIV — COURSE DELIVERY SYSTEM

Chapter 70 — Virtual Course Format

70.1 Course Length

70.2 Session Length

70.3 Session Frequency

70.4 Zoom Setup

70.5 Student Materials

70.6 Student Preparation

70.7 Live Demonstrations

70.8 Breakout Activities

70.9 Student Practice

70.10 Assignment Submission

70.11 Instructor Feedback

70.12 Completion

Chapter 71 — In-Person Course Format

71.1 Classroom Requirements

71.2 Equipment Requirements

71.3 Room Configuration

71.4 Demonstration Area

71.5 Student Practice Stations

71.6 Group Exercises

71.7 Individual Coaching

71.8 Recording Exercises

71.9 Classroom Materials

71.10 In-Person Completion

PART XXXV — COURSE SUPPORT MATERIALS

Chapter 72 — Student Resources

72.1 Workbook

72.2 Gear Guide

72.3 Software Guide

72.4 Prompt Library

72.5 Checklists

72.6 Templates

72.7 Content Calendar

72.8 Script Templates

72.9 Shot Lists

72.10 Production SOPs

72.11 Publishing SOPs

72.12 AI SOPs

Chapter 73 — Instructor Resources

73.1 Master Curriculum

73.2 Instructor Manual

73.3 Presenter Scripts

73.4 Slide Decks

73.5 Demonstration Files

73.6 Example Videos

73.7 Assignment Rubrics

73.8 Feedback Forms

73.9 Attendance Records

73.10 Certification Records

PART XXXVI — CAMERA V1 MASTER ASSESSMENT

Chapter 74 — Student Capability Assessment

74.1 Strategy

74.2 Audience

74.3 Content

74.4 On-Camera Performance

74.5 Technical Production

74.6 Editing

74.7 Publishing

74.8 Repurposing

74.9 AI Utilization

74.10 Sustainability

PART XXXVII — CAMERA V1 FINAL IMPLEMENTATION PACKAGE

Chapter 75 — The Student’s Finished System

75.1 Business Content Strategy

75.2 Character Definition

75.3 Audience Profile

75.4 Monetization Map

75.5 Content Pillars

75.6 Hook Library

75.7 Script Library

75.8 Gear Configuration

75.9 Software Configuration

75.10 Recording Setup

75.11 Editing Workflow

75.12 Repurposing System

75.13 AI Workflow

75.14 Publishing Calendar

75.15 Measurement System

75.16 30-Day Action Plan

75.17 90-Day Action Plan

APPENDICES

Appendix A — CAMERA Terminology Glossary

Appendix B — Video Production Glossary

Appendix C — Audio Glossary

Appendix D — Lighting Glossary

Appendix E — AI and LLM Glossary

Appendix F — Platform Terminology

Appendix G — Equipment Comparison Tables

Appendix H — Budget Shopping Lists

Appendix I — Phone-Only Setup Guide

Appendix J — Home Office Setup Guide

Appendix K — Professional Studio Setup Guide

Appendix L — Camera Settings Quick Reference

Appendix M — Lighting Diagrams

Appendix N — Audio Diagrams

Appendix O — Framing Diagrams

Appendix P — Shot List Templates

Appendix Q — Script Templates

Appendix R — Hook Templates

Appendix S — CTA Templates

Appendix T — Content Calendar Templates

Appendix U — Repurposing Templates

Appendix V — AI Prompt Library

Appendix W — AI Tool Evaluation Worksheet

Appendix X — Pre-Production Checklist

Appendix Y — Pre-Recording Checklist

Appendix Z — Recording Checklist

Appendix AA — Editing Checklist

Appendix AB — Publishing Checklist

Appendix AC — Weekly Content Checklist

Appendix AD — Monthly Content Review

Appendix AE — Student Self-Critique Form

Appendix AF — Instructor Evaluation Rubric

Appendix AG — Final Project Rubric

Appendix AH — Certificate Template

Appendix AI — Student Completion Record

CAMERA V1 — MASTER COURSE ASSET MAP

The Master TOC above becomes the controlling structure for every CAMERA V1 asset.

For each teaching chapter that is included in the live course, the build will ultimately contain:

1. MASTER BOOK CHAPTER

The complete educational treatment and permanent reference material.

2. STUDENT CHAPTER / HOME STUDY VERSION

The appropriate chapter or chapter section assigned for review outside class.

3. LIVE TEACHING SCRIPT

The condensed instructor-facing teaching version—not a summary and not a webinar script.

4. CLIENT-FACING SLIDES

Visual teaching support containing the concepts, demonstrations, diagrams, examples, exercises, and reference information students need to see.

5. INSTRUCTOR PROMPTER

Full spoken teaching language corresponding slide-by-slide with the presentation.

6. LIVE EXERCISES

Activities students actually perform during the session.

7. HOMEWORK / IMPLEMENTATION ASSIGNMENT

Work that moves the student’s own business forward.

8. WORKBOOK PAGES

The corresponding student worksheets and implementation tools.

9. CHECKLISTS / SOPs

Practical tools students can use after the course.

10. INSTRUCTOR NOTES

Timing, demonstrations, anticipated questions, teaching cautions, and transition instructions.

11. ASSESSMENT

The method for determining whether the student actually learned and implemented the material.

12. COMPLETION REQUIREMENT

The measurable requirement for that section or module.

CAMERA V1 — CORE TEACHING ARCHITECTURE

The course should not attempt to teach every chapter above during a single short webinar.

The Master TOC is the entire CAMERA knowledge system.

The actual paid course will select and sequence the appropriate chapters into 4–6 substantial live educational sessions, with each session capable of running approximately 60–120 minutes depending on the final curriculum and audience.

The student receives selected book chapters for home-study reinforcement, while the live course concentrates on:

TEACH → DEMONSTRATE → PRACTICE → CORRECT → IMPLEMENT

That distinc

# CAMERA™ V1: Live Virtual Course & Self-Guided Platform Implementation Blueprint

Prepared for: John Carr | Carr Multimedia / LEGAiSEE

Course Architecture: CAMERA™ Authority Media Training System (V1)

Purpose: Comprehensive workflow and technical execution guide for reducing the 58-Chapter Master Textbook into a 10–12 hour live Zoom masterclass, generating professional prompter/presenter scripts, creating cinematic AI slide decks, and architecting a secure, anti-piracy self-guided course-hosting platform.

## SECTION 1: Curriculum Reduction Workflow (58 Chapters → 10–12 Hour Live Zoom Course)

To transform a comprehensive 58-chapter textbook into a high-value, high-fee live virtual masterclass (10–12 total hours, structured across 4 to 6 sessions of 2 hours each), you must pivot from an exhaustive reference manual to an implementation-focused operational architecture.

### The 4-Module Live Architecture (12 Hours Total)

Instead of teaching every single sub-chapter, group the material into four high-impact execution modules following your core teaching model: TEACH → DEMONSTRATE → PRACTICE → CORRECT → IMPLEMENT.

- Module 1: Strategy, Character & Audience (The Blueprint) — 3 Hours

  - Core Textbook Sources: Chapters 1–3 (Foundation), Chapters 4–5 (Character & Presence), Chapters 6–7 (Audience & Serving), Chapters 8–9 (Monetization & Strategy).

  - Live Focus: Diagnosing the business need, defining authentic authority on camera, mapping content pillars to monetization, and eliminating corporate stiffness.

- Module 2: The Engagement & Delivery Engine (The Performance) — 3 Hours

  - Core Textbook Sources: Chapters 10–12 (Attention & Hooks), Chapters 13–14 (Voice, Rhythm & Delivery), Chapters 32–34 (Practicals).

  - Live Focus: Constructing 3-second pattern-interrupt hooks, internalizing scripts instead of memorizing them, eliminating vocal filler, and live delivery practice.

- Module 3: The Technical Standard & AI Acceleration (The Studio & Workflow) — 3 Hours

  - Core Textbook Sources: Chapters 15–18 (Camera, Lighting, Background, Audio), Chapters 29–31 (AI in Content Workflow, LLMs), Chapters 47–49 (Gear).

  - Live Focus: Audio-first philosophy, building a clean room/office acoustic setup, setting up $0–$500 configurations, and leveraging LLMs for rapid scripting and repurposing without losing personal voice.

- Module 4: Editing, Repurposing & Operations (The System) — 3 Hours

  - Core Textbook Sources: Chapters 19–20 (Repurposing & Workflows), Chapters 21–22 (Editing), Chapters 23–28 (Platforms), Chapters 41–42 (Operations).

  - Live Focus: The 1-to-many content model (turning 1 long video into 10 assets), basic cuts and captions, choosing the right platform (YouTube/LinkedIn), and establishing a sustainable weekly 2-hour operating cycle.

## SECTION 2: Presenter Scriptwriting Workflow

Writing your live instructor scripts directly from the textbook chapters requires an operational translation format. You need a script that balances cinematic authority with conversational engagement.

### The 4-Column Script Template (Markdown Table Format)

Use this structure for every slide/chapter translation in your Instructor Prompter System (Chapter 69):

| Slide # | Teaching Objective | Spoken Presenter Script (Exact Words) | Visual / Demo Action |
| --- | --- | --- | --- |
| 01-01 | Shift mindset from production agencies to internal capability. | "Stop paying production agencies $5,000 a month to rent your own voice back to you. Today, we build your internal media engine." | Display Chapter 1 Title Slide with subtle gold light sweep. |
| 01-02 | Expose the 'Start With the Camera' trap. | "Most businesses fail at content because they buy a $3,000 camera before they know what problem they are solving for their buyer." | Point to diagram: Business Goal → Audience → Camera. |

### Script Generation Prompts for LLMs

Feed your textbook chapters into an LLM using this strict prompt template to generate your presenter scripts:

Plaintext

You are the master instructor for the CAMERA™ Authority Media Training System.

Using the attached text from [Chapter X], write an instructor presenter script for a live Zoom class.

Tone: Serious, practical, intelligent, cinematic, authoritative (30-year broadcast veteran). NOT an influencer style.

Formatting rules: Write in conversational spoken prose meant to be spoken aloud. Include exact transitional phrases, cues for live demonstrations, and prompts to ask the virtual audience.

## SECTION 3: FREE AI Slide Deck Tools & Cinematic Workflows

To achieve a high-dollar, non-PowerPoint looking deck with animations using free tools, leverage modern web-based presentation engines that support cinematic typography, dark modes, and automated motion design.

### Best-Fit Free Tools & Pricing Options

| Tool | Best Used For | Free Tier Limits | Pro Pricing | Visual Style & Animations |
| --- | --- | --- | --- | --- |
| Gamma.app | Instant markdown-to-deck conversion, clean modern layouts, cards, and visual containers. | Generous free AI credits upon signup; watermark on free tier exports. | ~$10–$20/mo | Sleek, modern, non-PowerPoint, card-based responsive design with smooth UI transitions. |
| Beautiful.ai | Enforcing professional design constraints (dynamic scaling as you type). | Limited free trial; requires subscription for full export utility. | ~$12–$40/mo | Clean, corporate, mathematically balanced layouts that auto-adjust visual hierarchy. |
| Google Slides + Custom CSS/Layouts | Complete absolute control, zero cost, infinite export options. | 100% Free (Google Workspace). | Free | Traditional unless custom-animated; requires manual design skill to avoid looking generic. |
| Canva (Free Tier) | Cinematic templates, widescreen 16:9 cinematic framing, motion presets. | Massive free stock/templates; some assets require Pro. | ~$15/mo | Highly polished, highly graphic, cinematic text reveals and slide transitions. |

### Recommended Workflow for Cinematic Slides:

- The Text Prep: Export your reduced chapter outlines/scripts into clean markdown format.

- The Generation (Gamma.app): Paste your markdown into Gamma using a "Dark Cinematic / Professional Education" theme prompt. Let the AI generate the card structures, containers, and visual blocks.

- The Polish: Export the deck or present directly via browser in 16:9 widescreen mode to maintain crisp typography and fluid UI animations.

## SECTION 4: Course Creation, Hosting & Anti-Piracy Architecture (Self-Guided 58-Chapter Master Course)

To host your full 58-chapter end-to-end master textbook, workbooks, video modules, and downloadable assets with enterprise-grade security and automated checkout, you need a dedicated hosting stack.

### Platform Comparison Matrix

| Platform | Best For | Security & Anti-Piracy | Payment & Access Automation | Estimated Monthly Cost |
| --- | --- | --- | --- | --- |
| Kajabi | All-in-one business courses, clean UI, integrated email and checkouts. | Standard password protection, single-device login monitoring plugins, encrypted video streaming via Wistia/Vimeo integration. | Built-in Stripe/PayPal checkout, instant automated login creation. | ~$149 – $399/mo |
| Teachable / Thinkific | Dedicated course creators with robust student progress tracking. | Content encryption, disable right-click, PDF stamping (student email watermarking on downloads). | Automated enrollment, coupon management, affiliate payouts. | ~$39 – $149/mo + transaction fees (on lower tiers) |
| WordPress + LearnDash + MemberPress | Ultimate ownership, zero platform lock-in, advanced custom access rules. | High customizability: integrate Video Encryption plugins (e.g., Bunny.net Stream with token-authenticated signed URLs), IP restriction plugins, and dynamic PDF watermarking. | WooCommerce or Stripe Webhooks for instant automated user account generation upon purchase. | ~$15 – $40/mo (Hosting + plugin licenses) |

### Anti-Piracy & Security Protocols for High-Value B2B Content

- Encrypted Video Streaming: Never host raw MP4 files on open servers. Use Bunny.net Stream or Vimeo Enterprise with domain-lock embedding so videos cannot be downloaded via browser extensions or inspected elements.

- Dynamic PDF Watermarking: Stamp the purchasing business name and buyer’s IP/Email address dynamically across every page of the 58-Chapter Master Textbook and Workbook PDFs upon download.

- Session & IP Limits: Configure membership logins to flag or restrict simultaneous multi-state logins using membership plugins like MemberPress.

## SECTION 5: Comprehensive Cost & Profit Margin Analysis (Zoom Live vs. Self-Guided)

To maximize your profit margin while generating cash flow quickly during unemployment:

### Phase 1: The Live Zoom Masterclass (Immediate Cash Flow)

- Format: 4-Session Live Virtual Masterclass (12 Hours total) + Workbook.

- Target Price per Business Seat: $995 – $1,495 (Positioned as a corporate training investment that replaces a $5,000/mo agency).

- Capacity: 10 to 20 businesses per cohort.

- Your Cost: $0 (Using Zoom, free AI slide tools, Google Docs/Sheets).

- Gross Margin: Nearly 100% (minus standard payment processing fees like Stripe's ~2.9% + $0.30).

### Phase 2: The Automated Self-Guided Master Course (Passive Scale)

- Format: Self-paced access to the full 58-Chapter Master Textbook, video modules, and prompt library.

- Target Price: $497 – $797 per license.

- Platform Cost: $49–$149/mo (Teachable or self-hosted WordPress).

What chapters form the core 10 hour live course curriculum

The CAMERA™ V1 10–12 hour live virtual masterclass extracts and concentrates the most essential operational chapters from your 58-chapter master textbook.

Organized across 4 intensive sessions (approx. 3 hours each), this curriculum cuts out heavy reference theory and focuses entirely on the core model: TEACH → DEMONSTRATE → PRACTICE → CORRECT → IMPLEMENT.

### Module 1: Strategy, Character & Audience (Session 1 — 3 Hours)

Focus: Diagnosing the business need, defining authentic authority on camera, and understanding buyer psychology.

- Part I — CAMERA System Foundation

  - Chapter 1 — What CAMERA Is (Focus: 1.7 Internal Capability vs. 1.11 "Start With What You Have" Principle)

- Part II — The CAMERA Operating Model

  - Chapter 2 — The CAMERA Framework (Focus: 2.1 The Six Dimensions & 2.11 Content vs. Marketing)

- Part III — Business Content Diagnosis

  - Chapter 3 — Determine What Your Business Actually Needs (Focus: 3.2 Start With the Business, 3.18 Choosing the Appropriate Content Model, 3.19 Minimum Viable Content Operation)

- Part IV — C: Character

  - Chapter 4 — Character: Who Is On Camera? (Focus: 4.2 Authentic Authority, 4.3 Business Owner/Founder as Authority, 4.10 Experience & Knowledge as Content)

  - Chapter 5 — On-Camera Presence (Focus: 5.3 Eye Line, 5.11 Confidence, 5.12 Authority, 5.15 Avoiding Talking Head Syndrome)

- Part V — A: Audience

  - Chapter 6 — Understanding the Person Watching (Focus: 6.3 Buyer vs. Viewer, 6.5 Audience Intent, 6.10 Objections)

  - Chapter 7 — Content That Serves the Audience (Focus: 7.1 Education vs. Promotion, 7.3 Solving Problems, 7.7 Building Trust Through Useful Information)

- Part VI — M: Monetization

  - Chapter 8 — Connecting Content to the Business (Focus: 8.3 Mapping Content to Offers, 8.8 Lead Generation, 8.15 Calls to Action)

### Module 2: The Engagement & Delivery Engine (Session 2 — 3 Hours)

Focus: Stopping the scroll, internalizing scripts instead of memorizing them, and mastering on-camera delivery.

- Part VII — E: Engagement

  - Chapter 10 — Understanding Attention (Focus: 10.1 Economics of Attention, 10.5 First Three Seconds, 10.11 Pattern Interrupts)

  - Chapter 11 — Hook Construction (Focus: 11.1 Problem Hook, 11.4 Contrarian Hook, 11.8 "You Are Doing This Wrong" Structure)

  - Chapter 12 — Retention and Delivery (Focus: 12.2 Information Density, 12.3 Pacing, 12.11 Open Loops)

- Part VIII — On-Camera Delivery

  - Chapter 13 — Speaking Naturally (Focus: 13.1 Memorization vs. Internalization, 13.4 Conversational Delivery, 13.7 Teleprompters)

  - Chapter 14 — Voice, Rhythm and Authority (Focus: 14.4 Pace, 14.7 Pausing, 14.9 Eliminating Vocal Filler)

- Part XVII — Content Creation Practicals

  - Chapter 32 — Building a Video From Scratch (Focus: End-to-end framework walk-through)

  - Chapter 33 — The 60-Second Authority Video (Focus: Live drafting and rapid student breakdown)

### Module 3: Technical Standards & AI Acceleration (Session 3 — 3 Hours)

Focus: Audio-first production, building a clean studio/office space on a budget, and leveraging LLMs for rapid scripting.

- Part IX — Camera and Visual Foundations

  - Chapter 15 — The Camera (Focus: 15.1 Phone vs. Webcam vs. Dedicated Camera, 15.11 Horizontal vs. Vertical, 15.15 Camera Placement)

- Part X — Lighting

  - Chapter 16 — Making People Look Better (Focus: 16.2 Quality/Direction of Light, 16.5 Natural Window Light, 16.8 Three-Point Lighting)

- Part XI — Background and Set Design

  - Chapter 17 — What the Camera Sees Behind You (Focus: 17.1 Background as Communication, 17.5 Clutter, 17.18 Building a Repeatable Set)

- Part XII — Audio

  - Chapter 18 — Sound Is Half the Picture (Focus: 18.1 Why Audio Matters More Than Camera, 18.2 Room Acoustics/Echo, 18.8 Wireless Lavalier Systems, 18.12 Microphone Placement)

- Part XVI — A: AI Acceleration

  - Chapter 29 — AI in the Modern Content Workflow (Focus: 29.3 AI as a Tool, 29.6 The AI-Assisted Workflow, 29.10 Script Drafting)

  - Chapter 30 — Working With LLMs (Focus: 30.4 Providing Source Material, 30.6 Giving AI Constraints, 30.15 Reusable Prompt Systems)

  - Chapter 31 — Avoiding the AI Tool Trap (Focus: 31.2 Tools vs. Workflow, 31.3 Free Tools First)

- Part XXIV — Gear System

  - Chapter 47 — Gear Philosophy (Focus: 47.1 Buy for the Problem, 47.3 Phone First, 47.4 Audio First)

  - Chapter 48 — Budget Gear Configurations (Focus: 48.1 $0–$100 Setup, 48.3 $250–$500 Setup)

### Module 4: Editing, Repurposing & Operations (Session 4 — 3 Hours)

Focus: The 1-to-many repurposing model, basic cuts/captions, channel selection, and building a sustainable weekly workflow.

- Part XIII — R: Repurposing

  - Chapter 19 — One Idea, Multiple Assets (Focus: 19.1 Repurposing Principle, 19.3 Master Content Asset, 19.4 Long-Form to Short-Form, 19.14 1-to-Many Model)

  - Chapter 20 — Building the Content Production Workflow (Focus: 20.20 Weekly Content Operating Cycle)

- Part XIV — Editing

  - Chapter 21 — Editing for the Modern Business (Focus: 21.2 Cutting Dead Time, 21.5 Pacing, 21.6 Captions, 21.14 Keeping Editing Invisible)

  - Chapter 22 — Editing Software (Focus: 22.3 CapCut, 22.8 Descript, 22.9 Choosing One Primary Editor)

- Part XV — Platform Mastery

  - Chapter 23 — YouTube (Focus: 23.2 Long-Form Authority, 23.6 Titles, 23.7 Thumbnails)

  - Chapter 24 — LinkedIn (Focus: 24.1 Professional Authority, 24.2 Founder Content)

  - Chapter 28 — Other Distribution Channels (Focus: 28.1 Email, 28.3 Landing Pages)

- Part XX — Content Operations

  - Chapter 41 — Building the Internal Content Department (Focus: 41.11 One Person Wearing Multiple Roles)

  - Chapter 42 — Content Management (Focus: 42.1 Content Calendar, 42.5 Content Database)

What about giving LLM the revised presenter script, and have llm just create web page code to host a multiple page/page target "teaching site" on my server, vs the usual card route?

Building a custom web-based "teaching site" or cinematic presentation application via LLM-generated HTML/CSS/JS is an exceptional approach. Given your technical background and experience building local web apps and databases, this completely bypasses generic slide software constraints, eliminates monthly SaaS tool fees, and delivers a jaw-dropping, high-dollar aesthetic.

Instead of a rigid PowerPoint deck or a generic course platform UI, you get a custom-branded, dark-mode, cinematic web application that serves a dual purpose:

- The Live Zoom Presentation Deck: You share your browser screen and click through clean, responsive, interactive modules styled like a high-end tech platform or digital magazine.

- The Self-Guided Student Hub: The exact same codebase can be deployed to your server behind a secure login or access token for your self-paced buyers.

### The Recommended Tech Stack (Zero Build Tools Required)

To keep deployment frictionless (running straight from your own server or a local test environment), avoid complex React or Node.js build pipelines. Instead, instruct the LLM to use a Zero-Build CDN Stack:

- HTML5 / Semantic Markup: Clean, structured document layout.

- Tailwind CSS (via CDN): Gives the LLM instant access to professional styling, dark mode (bg-zinc-950), custom gold accents, grid layouts, and smooth responsive design without needing a compiler.

- Alpine.js (via CDN): Adds lightweight interactivity (tab switching, collapsible modules, mobile navigation, slide pagination) without heavy JavaScript frameworks.

- Lucide Icons or FontAwesome (via CDN): For clean, professional UI iconography.

### Workflow: How to Prompt the LLM to Build Your Teaching Site

Instead of asking for "a webpage," give the LLM strict architectural constraints to generate a Single-Page Application (SPA) with multi-view tabs or slide-deck mode.

#### Step 1: Generate the Master Layout & Shell

Paste this prompt into your LLM to create the foundational template:

Plaintext

You are an expert front-end developer and cinematic UI designer.

Write a complete, single-file HTML application (using Tailwind CSS and Alpine.js via CDN) that serves as the interactive master presentation and student hub for the CAMERA™ Authority Media Training System.

Design Requirements:

- Theme: Deep cinematic dark mode (zinc-900 / zinc-950 background, crisp white text, subtle gold/amber accent highlights #D4AF37).

- Typography: Clean sans-serif, high legibility, generous line spacing.

- Layout: A sidebar navigation for the 4 core modules, a main content display area with a toggle between "Presentation Mode" (large text, clean slides) and "Reading/Reference Mode" (full textbook chapters), and built-in progress tracking.

- Interactivity: Alpine.js state to handle switching modules, expanding chapters, and viewing embedded presenter notes.

Provide the complete, production-ready HTML file code in a single code block.

#### Step 2: Inject the Content & Presenter Notes

Once the shell is generated, feed your revised presenter scripts and chapter summaries chapter-by-chapter into the LLM with this instruction:

Plaintext

Update the previous HTML teaching site code by inserting the complete content, slide points, and presenter notes for Module 1 into the designated data structure or DOM sections. Ensure all formatting maintains the cinematic dark-mode aesthetic.

### Why a Custom Web App Beats Traditional Slides & LMS Platforms

| Feature | PowerPoint / Gamma | Traditional LMS (Kajabi/Teachable) | LLM-Generated Custom Web App |
| --- | --- | --- | --- |
| Visual Quality | Limited by templates or strict SaaS UI boundaries. | Generic video player + PDF download layout. | 100% Custom Cinematic Branding (Tailored typography, custom cards, dark/gold aesthetic). |
| Hosting Cost | Free / Software subscription. | $39 to $399/mo ongoing SaaS fee. | $0 (Hosted on your own existing server infrastructure). |
| Interactivity | Static slides or basic transitions. | Standard video embedding and comment sections. | Fully interactive calculators, checklists, toggles, and multi-view layouts. |
| Ownership | Locked to proprietary file types. | Locked to the platform ecosystem. | Total Code Ownership: You own every line of HTML/CSS, fully portable to any server. |

Want me to generate the complete HTML/Tailwind starter code for your teaching site?

Yes

Create a full end to end, step by step plan/to-do list with detailed instructions, llm prompts, etc to get from 0 today to final presentation ready zoom instruction site on my server, including setup and presentation operating instructions to present the pages but keep my script hidden etc. i want everything to be as automated/llm created as possible with the goal scheduling a full cohort as soon as possible... whatever that timeframe is. advise on best steps, best llms to use per step, best doccumentation/backup methods for sureserver/g-drive. again and end to end scope and execution step by step plan.

This is a complete, end-to-end master execution blueprint to take your CAMERA professional education platform from scratch to a production-ready Zoom instruction and presentation site hosted on your server.

The system features a dual-pane presentation dashboard: your audience sees clean widescreen cinematic modules on Zoom/screenshare, while you control the flow via a private view featuring integrated teleprompter scripts, live session controls, and timing pacing—completely hidden from viewers.

## Phase 1: Architecture & Model Selection Strategy

To build this rapidly and efficiently, deploy specialized frontier models for each distinct phase of execution:

| Phase | Task | Recommended LLM / Tool | Why |
| --- | --- | --- | --- |
| 1. Architecture & Scaffold | Generating file structures, server routing, and database config | Claude 4.5 Sonnet / Opus 4.8 | Exceptional multi-file system design and code coherence. |
| 2. UI & Front-End Design | Building widescreen layouts, CSS grid backdrops, and teleprompter sync | Gemini 2.5 Pro | Strong multi-modal UI sense and handling complex single-page app DOM states. |
| 3. Logic & Security | Server auth, session management, and backup scripts | GPT-5.5 (Codex / Terminal) | High format discipline and robust execution logic for backend handling. |

## Phase 2: Step-by-Step Execution Plan

1

Server Environment & Git Repository Bootstrap

Prerequisite: SSH access to your server

Initialize your production directory, secure environment variables, and set up the local-to-server sync pipeline.

Prompt to feed your LLM for this step:

"Generate a secure Node.js Express server setup (or a clean static Vite/React build structure depending on preference) configured for deployment on a Linux server via PM2. Include a .env.example file for session keys, an automated daily backup script that compresses public assets and database states into an encrypted .tar.gz, and an rsync config file to push local updates directly to my server."

2

Build the Core Presentation & Teleprompter App UI

The dual-pane engine

Create a single-page application (SPA) featuring a dual-view toggle: Audience View (widescreen cinematic cards, interactive modules) and Presenter View (the active script window, countdown timers, and slide progression controls).

Prompt to feed your LLM for this step:

"Write a modular React/Tailwind component layout for a presentation platform named CAMERA. It needs a URL parameter or keystroke toggle (e.g., ?mode=presenter) that switches between two layouts:

- Audience Mode: Clean, 16:9 cinematic widescreen presentation canvas with zero UI clutter.

- Presenter Mode: A split screen showing the current slide visual on the left, and a synchronized markdown teleprompter script panel on the right with adjustable auto-scroll speed, font scaling, and elapsed time counters. Ensure the presenter controls broadcast state updates via LocalStorage/BroadcastChannel API so clicking 'Next' on the presenter screen updates the audience window instantly without leaking UI elements to the main screen."

3

Zoom Integration & Screen Share Optimization

Locking down the viewport for clean streaming

Configure the application layout to fit standard video conferencing aspect ratios and eliminate browser chrome artifacts.

Prompt to feed your LLM for this step:

"Provide CSS/Tailwind utilities to lock the presentation viewport to a strict 16:9 ratio with letterboxing for odd screen resolutions. Include a 'Zoom Presentation Mode' toggle that hides all browser scrollbars, toolbars, and system cursors after 3 seconds of inactivity, ensuring a pristine feed when sharing screen via Zoom."

4

Server Deployment, Nginx, & SSL Configuration

Live URL setup on your server

Map your application to your server domain with secure reverse proxy routing.

Prompt to feed your LLM for this step:

"Write an Nginx server block configuration file that proxies requests to my local Node app running on port 3000, enables Gzip compression, sets up secure SSL headers via Certbot/Let's Encrypt, and restricts access to the /presenter route via a basic HTTP password or a secure JWT token cookie."

5

Automated Backup Configuration (Server & Google Drive)

Disaster recovery pipeline

Establish a bulletproof backup cadence syncing server snapshots to Google Drive.

Prompt to feed your LLM for this step:

"Write a complete automated shell script (backup.sh) that:

- Dumps any local SQLite/MySQL data.

- Archives the project directory and uploads directory into a timestamped .tar.gz file.

- Uses rclone to securely upload the archive to a designated Google Drive folder (CAMERA_Backups).

- Deletes local backups older than 7 days to preserve disk space. Include a crontab schedule entry to run this automatically every night at 2:00 AM."

## Phase 3: Launch & Cohort Scheduling Checklist

To move immediately toward booking your first live cohort, complete this checklist:

- [ ] Dry Run #1: Open the Audience view on an external monitor or second device, and the Presenter view on your primary display. Verify that script scrolling and slide transitions match seamlessly.

- [ ] Zoom Audio/Video Test: Launch a private Zoom meeting, share only the specific browser window running the Audience view, and test your mic routing. Confirm that your teleprompter notes and timer counters are invisible to the meeting participants.

- [ ] Content Injection: Populate your presentation modules and corresponding scripts into the markdown data structure generated in Phase 2.

- [ ] Cohort Booking Link: Deploy a simple landing page or schedule an automated intake link to capture registrations and distribute the private access parameters.

To refine this implementation further:

Generate the exact React code for the dual-pane presenter/audience app

Write the complete rclone and backup automation script

Gemini is AI and can make mistakes.

Searching the web

Autofill

;

Copy response

# GROK

CAMERA™ V1 — Live Zoom Course Condensation Plan

10–12 Hour Multi-Day Educational Course

Copy-paste ready for Google Docs.

### Governing Principles for Condensation

The Master TOC is the complete reference library (58+ chapters + workbook + instructor system).

The live course does not teach every chapter.

Live course goal (from your architecture):

TEACH → DEMONSTRATE → PRACTICE → CORRECT → IMPLEMENT

Students leave with a working internal content capability for their own business, not just knowledge.

Target structure:

4–6 live sessions totaling 10–12 hours.

Recommended: 5 sessions × 2–2.5 hours (or 4 sessions × 2.5–3 hours).

Each session includes teaching, live demo, student practice, feedback, and clear homework that advances their real business.

Home-study chapters from the full textbook reinforce each session.

### Recommended Live Course Structure

CAMERA™ Authority Media Training — Live Virtual Intensive

Total Live Time: ~11–12 hours

Format: 5 sessions over 2–3 weeks (or intensive 2-day format)

#### Session 1 — Foundation + Diagnosis (2.25 hours)

Core Goal: Students stop guessing and know exactly what their business actually needs.

Live Teaching Focus (from Master TOC):

- Chapter 1 (What CAMERA Is) – condensed

- Chapter 2 (CAMERA Framework – Six Dimensions overview)

- Chapter 3 (Business Content Diagnosis – full emphasis)

- Selected pieces of Chapters 4 & 6 (Character + Audience intro)

Session Flow:

- Opening & CAMERA philosophy (15 min)

- Six Dimensions overview + live mapping exercise (30 min)

- Business Content Diagnosis workshop (45 min) – students assess their own business type and content model

- Character + Audience quick definition (30 min)

- Implementation assignment briefing + Q&A (15 min)

Homework: Complete Workbook 1 + Workbook 2 + first draft of Character and Audience profiles.

Home-study chapters: 1, 2, 3, 4.1–4.10, 6.

#### Session 2 — Character + On-Camera Presence (2.25 hours)

Core Goal: Students look and sound like credible authorities on camera (not performers).

Live Teaching Focus:

- Chapter 4 (Character – deep)

- Chapter 5 (On-Camera Presence – full practical)

- Chapter 13 & 14 (Speaking Naturally + Voice/Rhythm – condensed)

Session Flow:

- Authentic Authority vs Persona (20 min)

- Defining the On-Camera Character workshop (25 min)

- Live on-camera presence training + framing, eye line, energy, stillness (50 min) – students practice on Zoom with instructor feedback

- Conversational delivery + recovering from mistakes (30 min)

- Assignment + Q&A (10 min)

Homework: Record 60-second authority video (raw, no editing). Self-assess using Chapter 5 checklist.

Home-study chapters: 4, 5, 13, 14.

#### Session 3 — Content That Converts + Engagement (2.5 hours)

Core Goal: Students create content that serves the audience and connects to revenue.

Live Teaching Focus:

- Chapter 7 (Content That Serves the Audience)

- Chapter 8 (Connecting Content to the Business)

- Chapter 9 (Content Strategy – pillars & priorities)

- Chapter 10 & 11 (Attention + Hook Construction – heavy practical)

Session Flow:

- Education vs Promotion + Content-to-Revenue mapping (30 min)

- Building Content Pillars workshop (25 min)

- Hook Construction deep dive + live workshop (50 min) – students write and refine 5 hooks

- Retention principles + first-frame/first-sentence practice (30 min)

- Assignment briefing (15 min)

Homework: Write 5 complete video scripts (60–90 seconds) using their pillars and hooks. Map each to a business outcome.

Home-study chapters: 7, 8, 9, 10, 11, 12.

#### Session 4 — Production System + AI Acceleration (2.5 hours)

Core Goal: Students can record, light, mic, and edit professional-looking content with what they already have (or minimal upgrades) + use AI effectively.

Live Teaching Focus:

- Chapters 15–18 (Camera, Lighting, Background, Audio – practical only)

- Chapter 20 (Content Production Workflow)

- Chapter 21–22 (Editing essentials)

- Chapters 29–31 (AI Acceleration – strong emphasis)

Session Flow:

- “Start With What You Have” + gear philosophy (15 min)

- Live setup demonstration (phone/webcam + lighting + audio) + troubleshooting (40 min)

- Minimal editing workflow demo (CapCut / Descript / Resolve free) (25 min)

- AI-assisted workflow (research → outline → script → hooks → captions → repurposing) live demo (40 min)

- Build your personal AI + production stack (20 min)

- Assignment (10 min)

Homework:

- Finalize personal gear/software configuration

- Record + edit one 60-second video using AI assistance

- Build reusable prompt system

Home-study chapters: 15–18, 20–22, 29–31, selected Gear chapters (47–49).

#### Session 5 — Implementation + Sustainable System (2–2.25 hours)

Core Goal: Students leave with a complete, working 30-day content system for their business.

Live Teaching Focus:

- Chapter 19 (Repurposing)

- Chapter 41–42 (Building Internal Content Operation – condensed)

- Chapter 43–44 (Measurement + Improvement Loop)

- Chapter 56 (Build Your Business Content System – the capstone)

Session Flow:

- One Idea → Many Assets system (25 min)

- Building the weekly operating cycle + calendar (25 min)

- Live construction of each student’s 30-day plan (45 min) – instructor coaching

- Measurement that matters + improvement loop (20 min)

- Final project briefing + certification path (15 min)

- Closing + next steps (10 min)

Final Project (required for certification):

Complete Chapter 56 deliverables:

Business Content Strategy, Character Definition, Audience Profile, Monetization Map, Content Pillars, Hook Library, Gear + Software Config, Recording Setup, Editing + Repurposing Workflow, AI Workflow, Publishing Calendar, Measurement Plan, 30-Day + 90-Day Action Plans.

Home-study chapters: 19, 20, 41–44, 56, selected platform chapters as needed (23–28).

### Time Allocation Summary

| Session | Focus | Live Hours | Primary Chapters |
| --- | --- | --- | --- |
| 1 | Foundation + Diagnosis | 2.25 | 1, 2, 3, 4, 6 |
| 2 | Character + On-Camera Presence | 2.25 | 4, 5, 13, 14 |
| 3 | Content Strategy + Engagement | 2.5 | 7, 8, 9, 10, 11, 12 |
| 4 | Production + AI | 2.5 | 15–18, 20–22, 29–31 |
| 5 | Implementation + Sustainability | 2.0–2.25 | 19, 41–44, 56 |
| Total |  | 11.5–12 | Core high-impact only |

Remaining chapters stay in the full Master Textbook for self-paced reference or advanced modules later.

### Next Steps in the Workflow

- Confirm or adjust this session structure (I can expand any session into full teaching outline + timing).

- I will write the full Live Teaching Scripts (instructor-facing, slide-by-slide prompter style) for each session.

- Then generate the Client-Facing Slide Deck structure and recommend the best free/low-cost AI tools for high-quality non-PowerPoint visuals with animations.

- Parallel track: Full 58-chapter self-paced course hosting recommendations with security/anti-piracy.

Would you like me to proceed with writing the detailed Live Teaching Script for Session 1 first, or adjust the session structure before continuing?